## Sheet1
Task Name | Duration | Planned Start Date | Planned End Date | Actual Start Date | Actual End Date | Status | Commetns | Actions Performed
Emergency Release
OQ Completion |  | 2018-12-24 | 2018-12-28 | 2018-12-24 |  | We are in the third round of OQ formal execution | Below three reasons caused for the delay 1. Time line was very aggressive * Within 3 Days prepared OQs for 9 user stories with limited application knowledge. 2. Not been provided scope for dry run 3. Improper technical review by DEV and BA 4. Missing scenarios should have caught in technical review. First Round of Execution: 1. Found Missing scenarios script defects and failed most of the scripts in the initial stage of the execution only. 2. Found one Functional Defect as well Second Round of Execution: 1. As we failed most of the script in first round of execution in the initail stage itself, found script defects related to the workflows and typo. 2. Found one Functional Defect | 1. Updated missing scenarios 2. Updated the scripts errors which all found in the second round of the execution.