## Sheet3
Country | Common Cases | Specific Cases | EBX Cases | Total
Italy | 50 | 70 | 15 | 85
France |  | 70 | 15 | 85
Brazil |  | 70 | 15 | 85
Australia |  | 70 | 15 | 85
UK |  | 70 | 15 | 85
Spain |  | 70 | 15 | 85
Regression | 30% of total test cases for Release 1 |  |  | 70
560
Month | No of resources | Activity | Rate in CHF
April | 1 | Test planning , strategy , req gathering etc | 4600
May | 5 | Authoring | 19180
June | 5 | Authoring & Dry run execution | 19180
Jul | 8 | Dry run and Formal Test execution | 30560
Aug | 8 | Formal Test execution & Regression & UAT support | 30560
Sep | 2 | Go Live Support | 4550
108630
20% |  |  | 21726
| Total |  | 130356
Assumptions
Assuming all contries will be deployed at once hence combined cases will be executed at a shot
Test case execution in 2 cycles - Dry run and Formal run
Regression cases assumed 30% of the actual
This includes retest for defect fixings and regression execution
Considered average 20 working days per Month

## Sheet1
Phases | No # of planned Test cases
EBX5 - UI verification | 70
Pre Migration | 10
Post Migration | 30
Integration | 40
Total number of Planned Test Cases | 150
|  | Month | Planned Tasks
|  | March | OQ scripting for 3 modules
Clarifications from buisness
|  | April | Dry run
Scirpt changes identified in dry run
Upload in to QC
Route to Review
Review comments will be incorporated
Approved test cases
|  | May | Test data preparation
OQ Execution round 1
route to approval
Test run reivewes should be fixed if anyu
OQ Execution (defects and failed cases) Round 2
route to approval
UAT Coordination