## OQ - Pivot
Count of Run Name | Column Labels
Row Labels | Approved | Obsolete | Grand Total
1 | 69 | 10 | 79
IQ
Passed | 3 |  | 3
OQ
Failed | 26 | 1 | 27
Not Completed |  | 8 | 8
Passed | 40 | 1 | 41
2 | 12 | 1 | 13
IQ
Passed | 1 |  | 1
OQ
Failed | 2 |  | 2
Not Completed |  | 1 | 1
Passed | 9 |  | 9
3 | 2 |  | 2
Grand Total | 83 | 11 | 94

## OQ Data
Execuion Round | Script Type | Run ID | Run Name | Test: Test Name | Configuration: Name | Execution Status | Tester | Exec Date | Exec Time | Approval Status | Reason
1 | IQ | 2 | Run_10-30_15-29-51 | Rollback IQ | Rollback IQ | Passed | beundor1 | 2018-10-30 | 7:53:16 PM | Approved
1 | IQ | 3 | Run_10-30_20-27-47 | GDD Platform IQ | GDD Platform IQ | Passed | beundor1 | 2018-10-31 | 2:14:21 PM | Approved
1 | IQ | 4 | Run_10-31_15-5-51 | GDD - Web IQ | GDD - Web IQ | Passed | beundor1 | 2018-10-31 | 4:54:14 PM | Approved
1 | OQ | 5 | Run_11-5_19-33-33 | 40-01 Access Rights check | 40-01 Access Rights check | Failed | schulmig | 2018-11-06 | 7:50:58 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 6 | Run_11-6_20-9-18 | 40-02 BR WF-18 | 40-02 BR WF-18 | Passed | schulmig | 2018-11-09 | 3:50:43 PM | Approved
1 | OQ | 8 | Run_11-7_14-27-12 | 40-03 Data Model check | 40-03 Data Model check | Failed | schulmig | 2018-11-07 | 6:51:25 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 9 | Run_11-7_18-53-17 | 40-04 BR WF-22 | 40-04 BR WF-22 | Failed | schulmig | 2018-11-07 | 7:29:08 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 10 | Run_11-7_19-33-53 | 40-05 Reference List Creation button | 40-05 Reference List Creation button | Passed | schulmig | 2018-11-07 | 7:39:32 PM | Approved
1 | OQ | 11 | Run_11-7_19-58-1 | 40-06 BR-WF 01 | 40-06 BR-WF 01 | Passed | schulmig | 2018-11-07 | 8:04:43 PM | Approved
1 | OQ | 12 | Run_11-7_20-5-44 | 40-07 BR WF-14 | 40-07 BR WF-14 | Not Completed | schulmig | 2018-11-07 | 8:05:48 PM | Obsolete | Run was cancelled on purpose as the tester needed a clarification
1 | OQ | 13 | Run_11-7_20-21-52 | 40-08 BR WF-19 | 40-08 BR WF-19 | Passed | schulmig | 2018-11-07 | 8:33:14 PM | Approved
1 | OQ | 14 | Run_11-7_20-34-31 | 40-09 Options to launch the deletion by SDS | 40-09 Options to launch the deletion by SDS | Passed | schulmig | 2018-11-07 | 8:41:01 PM | Approved
1 | OQ | 15 | Run_11-7_20-55-34 | 40-10 Reference Data List - Deletion Request - Accepted by SDS & Rejected by SME | 40-10 Reference Data List - Deletion Request - Accepted by SDS & Rejected by SME | Not Completed | schulmig | 2018-11-07 | 8:55:38 PM | Obsolete | Run was cancelled on purpose as the tester needed a clarification
1 | OQ | 16 | Run_11-7_21-24-40 | 40-11 Reference Data List - Deletion Request - Accepted by SDS & SME | 40-11 Reference Data List - Deletion Request - Accepted by SDS & SME | Not Completed | schulmig | 2018-11-07 | 9:24:43 PM | Obsolete | Run was cancelled on purpose as the tester needed a clarification
1 | OQ | 17 | Run_11-7_21-47-9 | 40-12 Reference Data List - Deletion Request - Record Locked | 40-12 Reference Data List - Deletion Request - Record Locked | Passed | schulmig | 2018-11-07 | 9:55:46 PM | Approved
1 | OQ | 18 | Run_11-7_21-57-27 | 40-13 Reference Data List - Deletion Request - Rejected by SDS | 40-13 Reference Data List - Deletion Request - Rejected by SDS | Not Completed | schulmig | 2018-11-07 | 9:57:30 PM | Obsolete | Run was cancelled on purpose as the tester needed a clarification
1 | OQ | 19 | Run_11-8_14-17-44 | 40-41 BR WF-10 | 40-41 BR WF-10 | Failed | kassaam4 | 2018-11-09 | 10:39:32 AM | Approved | Code Issues
1 | OQ | 21 | Run_11-8_15-50-17 | 40-61 Historization | 40-61 Historization | Failed | roberfr5 | 2018-11-08 | 4:27:45 PM | Approved | Code Issues
1 | OQ | 22 | Run_11-8_15-51-53 | 40-16 Reference Data List Creation - Rejected by SDS | 40-16 Reference Data List Creation - Rejected by SDS | Failed | schulmig | 2018-11-08 | 4:13:00 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 23 | Run_11-8_16-22-5 | 40-14 Reference Data List Creation - Accepted by SDS & Rejected by SME | 40-14 Reference Data List Creation - Accepted by SDS & Rejected by SME | Passed | schulmig | 2018-11-08 | 5:03:36 PM | Approved
1 | OQ | 24 | Run_11-8_17-4-5 | 40-15 Reference Data List Creation - Accepted by SDS & SME | 40-15 Reference Data List Creation - Accepted by SDS & SME | Failed | schulmig | 2018-11-08 | 5:27:20 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 25 | Run_11-8_17-4-22 | 40-62 Search options | 40-62 Search options | Passed | roberfr5 | 2018-11-08 | 5:30:04 PM | Approved
1 | OQ | 26 | Run_11-8_17-36-16 | 40-20 Reference Data List Creation - Golden definition - Rejected by SDS | 40-20 Reference Data List Creation - Golden definition - Rejected by SDS | Failed | kassaam4 | 2018-11-08 | 7:00:42 PM | Approved | Code Issues
1 | OQ | 27 | Run_11-8_19-5-39 | 40-19 Reference Data List Creation - Golden definition - Record locked | 40-19 Reference Data List Creation - Golden definition - Record locked | Passed | kassaam4 | 2018-11-14 | 3:21:59 PM | Approved
1 | OQ | 28 | Run_11-8_19-57-1 | 40-18 Reference Data List Creation - Golden definition - Accepted by SDS & Rejected by SME | 40-18 Reference Data List Creation - Golden definition - Accepted by SDS & Rejected by SME | Passed | kassaam4 | 2018-11-14 | 11:42:32 AM | Approved
1 | OQ | 29 | Run_11-8_20-47-11 | 40-17 Reference Data List Creation - Golden definition - Accepted by SDS & SME | 40-17 Reference Data List Creation - Golden definition - Accepted by SDS & SME | Passed | kassaam4 | 2018-11-14 | 3:06:00 PM | Approved
1 | OQ | 32 | Run_11-9_10-48-7 | 40-42 BR WF-13 | 40-42 BR WF-13 | Passed | kassaam4 | 2018-11-09 | 11:03:29 AM | Approved
1 | OQ | 33 | Run_11-9_11-4-7 | 40-43 BR WF-02 | 40-43 BR WF-02 | Passed | kassaam4 | 2018-11-09 | 11:13:11 AM | Approved
1 | OQ | 34 | Run_11-9_11-17-5 | 40-44 BR-GDD 01 | 40-44 BR-GDD 01 | Passed | kassaam4 | 2018-11-09 | 12:07:38 PM | Approved
1 | OQ | 35 | Run_11-9_12-8-28 | 40-45 BR GDD 03 | 40-45 BR GDD 03 | Passed | kassaam4 | 2018-11-09 | 12:16:00 PM | Approved
1 | OQ | 36 | Run_11-9_12-16-39 | 40-46 BR GDD 04 | 40-46 BR GDD 04 | Failed | kassaam4 | 2018-11-09 | 12:47:06 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 37 | Run_11-9_12-47-40 | 40-47 BR GDD 05 | 40-47 BR GDD 05 | Not Completed | kassaam4 | 2018-11-09 | 12:47:43 PM | Obsolete | Run was cancelled on purpose as the tester needed a clarification
1 | OQ | 38 | Run_11-9_12-48-49 | 40-47 BR GDD 05 | 40-47 BR GDD 05 | Passed | kassaam4 | 2018-11-09 | 12:55:04 PM | Approved
1 | OQ | 39 | Run_11-9_13-2-46 | 40-48 BR GDD 06 | 40-48 BR GDD 06 | Passed | kassaam4 | 2018-11-09 | 1:08:06 PM | Approved
1 | OQ | 41 | Run_11-9_13-11-2 | 40-49 BR GDD 07 | 40-49 BR GDD 07 | Passed | kassaam4 | 2018-11-13 | 9:48:03 AM | Approved
1 | OQ | 42 | Run_11-9_16-10-28 | 40-21 Reference Data List Creation - Pivot definition - Record Locked | 40-21 Reference Data List Creation - Pivot definition - Record Locked | Failed | schulmig | 2018-11-09 | 4:46:35 PM | Obsolete | Run was cancelled on purpose as the tester needed a clarification
1 | OQ | 43 | Run_11-9_16-47-39 | 40-22 Reference Data List Creation - Pivot definition - Rejected by SDS | 40-22 Reference Data List Creation - Pivot definition - Rejected by SDS | Failed | schulmig | 2018-11-09 | 5:36:31 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 44 | Run_11-9_17-37-0 | 40-23 Reference Data List Creation - Pivot defintion - Accepted by SDS & Rejected by SME | 40-23 Reference Data List Creation - Pivot defintion - Accepted by SDS & Rejected by SME | Passed | kassaam4 | 2018-11-14 | 5:04:02 PM | Approved
1 | OQ | 46 | Run_11-9_18-19-16 | 40-27 Reference Data List Update - Item Update (cancel creation) - Record Locked | 40-27 Reference Data List Update - Item Update (cancel creation) - Record Locked | Passed | schulmig | 2018-11-09 | 6:27:04 PM | Approved
1 | OQ | 47 | Run_11-9_18-27-34 | 40-28 Reference Data List Update - Item Update (cancel creation) - Rejected by DS | 40-28 Reference Data List Update - Item Update (cancel creation) - Rejected by DS | Failed | schulmig | 2018-11-09 | 6:35:35 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 48 | Run_11-9_18-35-48 | 40-24 Reference Data List Creation - Pivot defintion - Accepted by SDS & SME | 40-24 Reference Data List Creation - Pivot defintion - Accepted by SDS & SME | Passed | kassaam4 | 2018-11-14 | 6:07:42 PM | Approved
1 | OQ | 49 | Run_11-9_19-6-35 | 40-25 Reference Data List Update - Item Update (cancel creation) - Accepted by DS & Rejected by SDS | 40-25 Reference Data List Update - Item Update (cancel creation) - Accepted by DS & Rejected by SDS | Failed | schulmig | 2018-11-09 | 7:23:31 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 50 | Run_11-9_19-24-27 | 40-32 Reference Data List Update - Item Update (golden definition) - Record locked | 40-32 Reference Data List Update - Item Update (golden definition) - Record locked | Failed | schulmig | 2018-11-09 | 7:58:16 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 51 | Run_11-9_19-58-43 | 40-29 Reference Data List Update - Item Update (golden definition) - Rejected by DS | 40-29 Reference Data List Update - Item Update (golden definition) - Rejected by DS | Failed | kassaam4 | 2018-11-09 | 8:09:52 PM | Approved | Code Issues
1 | OQ | 52 | Run_11-9_20-10-53 | 40-30 Reference Data List Update - Item Update (golden definition) - Accepted by DS & Rejected by SDS | 40-30 Reference Data List Update - Item Update (golden definition) - Accepted by DS & Rejected by SDS | Failed | schulmig | 2018-11-09 | 8:53:32 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 54 | Run_11-9_20-56-53 | 40-31 Reference Data List Update - Item Update (golden definition) - Accepted by DS & SDS | 40-31 Reference Data List Update - Item Update (golden definition) - Accepted by DS & SDS | Failed | kassaam4 | 2018-11-14 | 12:53:49 PM | Approved | Code Issues
1 | OQ | 55 | Run_11-12_15-14-43 | 40-63 BR GDD 20 | 40-63 BR GDD 20 | Passed | roberfr5 | 2018-11-12 | 3:25:43 PM | Approved
1 | OQ | 56 | Run_11-12_15-41-12 | 40-64 BR GDD 21 | 40-64 BR GDD 21 | Passed | roberfr5 | 2018-11-12 | 5:14:13 PM | Approved
1 | OQ | 57 | Run_11-12_16-37-9 | 40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS | 40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS | Failed | kassaam4 | 2018-11-14 | 12:36:24 PM | Approved | Code Issues
1 | OQ | 58 | Run_11-12_16-49-33 | 40-35 Reference Data List Update - Item Update - Record Locked | 40-35 Reference Data List Update - Item Update - Record Locked | Passed | schulmig | 2018-11-12 | 5:12:44 PM | Approved
1 | OQ | 59 | Run_11-12_17-13-52 | 40-36 Reference Data List Update - Item Update - Rejected by DS | 40-36 Reference Data List Update - Item Update - Rejected by DS | Passed | kassaam4 | 2018-11-14 | 1:17:00 PM | Approved
1 | OQ | 60 | Run_11-12_18-15-39 | 40-33 Reference Data List Update - Item Update - Accepted by DS & Rejected by SDS | 40-33 Reference Data List Update - Item Update - Accepted by DS & Rejected by SDS | Passed | kassaam4 | 2018-11-14 | 2:25:53 PM | Approved
1 | OQ | 61 | Run_11-12_19-52-19 | 40-34 Reference Data List Update - Item Update - Accepted by DS and & SDS | 40-34 Reference Data List Update - Item Update - Accepted by DS and & SDS | Passed | kassaam4 | 2018-11-14 | 2:53:05 PM | Approved
1 | OQ | 62 | Run_11-12_20-35-52 | 40-40 Reference Data List Update - Record Locked | 40-40 Reference Data List Update - Record Locked | Passed | schulmig | 2018-11-12 | 8:45:25 PM | Approved
1 | OQ | 63 | Run_11-12_20-46-42 | 40-39 Reference Data List Update - Update Request - Rejected by SDS | 40-39 Reference Data List Update - Update Request - Rejected by SDS | Passed | kassaam4 | 2018-11-14 | 1:48:24 PM | Approved
1 | OQ | 64 | Run_11-12_21-35-1 | 40-38 Reference Data List Update - Update Request - Accepted by SDS & Rejected by SME | 40-38 Reference Data List Update - Update Request - Accepted by SDS & Rejected by SME | Failed | schulmig | 2018-11-12 | 9:46:56 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 65 | Run_11-12_21-48-33 | 40-37 Reference Data List Update - Update Request - Accepted by SDS & SME | 40-37 Reference Data List Update - Update Request - Accepted by SDS & SME | Passed | kassaam4 | 2018-11-14 | 1:38:03 PM | Approved
1 | OQ | 66 | Run_11-13_9-52-51 | 40-50 BR GDD 08 | 40-50 BR GDD 08 | Not Completed | kassaam4 | 2018-11-13 | 9:52:58 AM | Obsolete | Run was cancelled on purpose as the tester needed a clarification
1 | OQ | 67 | Run_11-13_11-8-42 | 40-51 BR GDD 09 | 40-51 BR GDD 09 | Passed | kassaam4 | 2018-11-13 | 12:00:49 PM | Approved
1 | OQ | 68 | Run_11-13_11-28-44 | 40-65 Data Transfer to MDM | 40-65 Data Transfer to MDM | Not Completed | roberfr5 | 2018-11-13 | 11:28:47 AM | Obsolete | Issue with Proton, hence had to cancel the script execution
1 | OQ | 69 | Run_11-13_14-1-14 | 40-66 System Connection to MDM through API GW | 40-66 System Connection to MDM through API GW | Passed | roberfr5 | 2018-11-13 | 2:29:18 PM | Obsolete | The tester had accidentally executed this script on dev environment as against being executed on QA environment
1 | OQ | 70 | Run_11-13_14-5-3 | 40-52 BR GDD 11 | 40-52 BR GDD 11 | Passed | kassaam4 | 2018-11-13 | 2:37:06 PM | Approved
1 | OQ | 71 | Run_11-13_14-38-26 | 40-53 BR GDD-12 | 40-53 BR GDD-12 | Failed | kassaam4 | 2018-11-13 | 4:39:16 PM | Approved | Code Issues
1 | OQ | 72 | Run_11-13_15-46-27 | 40-54 BR GDD 13 | 40-54 BR GDD 13 | Passed | schulmig | 2018-11-13 | 4:22:55 PM | Approved
1 | OQ | 73 | Run_11-13_16-40-10 | 40-56 BR GDD 15 | 40-56 BR GDD 15 | Passed | schulmig | 2018-11-13 | 4:50:26 PM | Approved
1 | OQ | 74 | Run_11-13_16-53-13 | 40-55 BR GDD 14 | 40-55 BR GDD 14 | Failed | schulmig | 2018-11-13 | 5:09:40 PM | Approved | Code Issues
1 | OQ | 75 | Run_11-13_16-54-2 | 40-60 BR GDD 19 | 40-60 BR GDD 19 | Passed | kassaam4 | 2018-11-13 | 5:05:16 PM | Approved
1 | OQ | 77 | Run_11-13_17-25-15 | 40-58 BR GDD 17 | 40-58 BR GDD 17 | Failed | kassaam4 | 2018-11-13 | 5:36:23 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 78 | Run_11-13_17-36-54 | 40-57 BR GDD 16 | 40-57 BR GDD 16 | Failed | kassaam4 | 2018-11-13 | 5:57:20 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 79 | Run_11-13_19-31-26 | 40-59 BR GDD 18 | 40-59 BR GDD 18 | Failed | schulmig | 2018-11-13 | 7:48:23 PM | Approved | Code Issues
1 | OQ | 80 | Run_11-13_19-51-51 | 40-07 BR WF-14 | 40-07 BR WF-14 | Failed | kassaam4 | 2018-11-13 | 8:03:00 PM | Approved | Script Error, OQ Script was modified
1 | OQ | 81 | Run_11-13_20-10-4 | 40-13 Reference Data List - Deletion Request - Rejected by SDS | 40-13 Reference Data List - Deletion Request - Rejected by SDS | Failed | kassaam4 | 2018-11-13 | 8:34:30 PM | Approved | Code Issues
1 | OQ | 82 | Run_11-13_20-40-26 | 40-10 Reference Data List - Deletion Request - Accepted by SDS & Rejected by SME | 40-10 Reference Data List - Deletion Request - Accepted by SDS & Rejected by SME | Passed | kassaam4 | 2018-11-14 | 11:03:48 AM | Approved
1 | OQ | 83 | Run_11-13_20-49-27 | 40-11 Reference Data List - Deletion Request - Accepted by SDS & SME | 40-11 Reference Data List - Deletion Request - Accepted by SDS & SME | Passed | kassaam4 | 2018-11-13 | 9:45:40 PM | Approved
1 | OQ | 84 | Run_11-13_22-19-33 | 40-21 Reference Data List Creation - Pivot definition - Record Locked | 40-21 Reference Data List Creation - Pivot definition - Record Locked | Passed | schulmig | 2018-11-13 | 10:36:37 PM | Approved
1 | OQ | 85 | Run_11-14_15-34-25 | 40-65 Data Transfer to MDM | 40-65 Data Transfer to MDM | Not Completed | KASSAAM4 | 2018-11-14 | 3:34:31 PM | Obsolete | Run was cancelled on purpose as the tester needed a clarification
1 | OQ | 86 | Run_11-14_15-37-6 | 40-66 System Connection to MDM through API GW | 40-66 System Connection to MDM through API GW | Passed | kassaam4 | 2018-11-15 | 11:52:30 AM | Approved
1 | OQ | 87 | Run_11-14_18-40-40 | 40-50 BR GDD 08 | 40-50 BR GDD 08 | Passed | kassaam4 | 2018-11-14 | 7:18:43 PM | Approved
1 | OQ | 89 | Run_11-15_15-20-56 | 40-65 Data Transfer to MDM | 40-65 Data Transfer to MDM | Failed | schulmig | 2018-11-15 | 6:50:51 PM | Approved | Code Issues
2 | IQ | 90 | Run_11-21_14-9-0 | GDD - Web IQ | GDD - Web IQ | Passed | beundor1 | 2018-11-21 | 2:41:21 PM | Approved
2 | OQ | 91 | Run_11-21_16-24-24 | 40-59 BR GDD 18 | 40-59 BR GDD 18 | Passed | schulmig | 2018-11-21 | 6:21:33 PM | Approved
2 | OQ | 92 | Run_11-21_16-52-3 | 40-53 BR GDD-12 | 40-53 BR GDD-12 | Passed | roberfr5 | 2018-11-21 | 6:03:56 PM | Approved
2 | OQ | 93 | Run_11-21_16-58-48 | 40-41 BR WF-10 | 40-41 BR WF-10 | Passed | kassaam4 | 2018-11-21 | 6:36:28 PM | Approved
2 | OQ | 94 | Run_11-21_18-25-35 | 40-13 Reference Data List - Deletion Request - Rejected by SDS | 40-13 Reference Data List - Deletion Request - Rejected by SDS | Passed | schulmig | 2018-11-21 | 6:57:30 PM | Approved
2 | OQ | 95 | Run_11-21_18-59-24 | 40-20 Reference Data List Creation - Golden definition - Rejected by SDS | 40-20 Reference Data List Creation - Golden definition - Rejected by SDS | Failed | schulmig | 2018-11-21 | 7:31:25 PM | Approved | Script Error, OQ Script was modified
2 | OQ | 96 | Run_11-21_19-33-3 | 40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS | 40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS | Not Completed | schulmig | 2018-11-21 | 7:33:06 PM | Obsolete | This was kept on hold by Tester 1 as he needed some clarificaiton. The tester 1 was later not available to continue the scirpt hence, this script was marked obsoleter
2 | OQ | 98 | Run_11-22_13-24-42 | 40-61 Historization | 40-61 Historization | Passed | kassaam4 | 2018-11-22 | 2:41:32 PM | Approved | Code Issues
2 | OQ | 99 | Run_11-22_14-42-50 | 40-65 Data Transfer to MDM | 40-65 Data Transfer to MDM | Passed | kassaam4 | 2018-11-23 | 12:00:47 PM | Approved
2 | OQ | 101 | Run_11-22_15-32-41 | 40-55 BR GDD 14 | 40-55 BR GDD 14 | Failed | kassaam4 | 2018-11-22 | 4:46:26 PM | Approved | Script Error, OQ Script was modified
2 | OQ | 102 | Run_11-22_18-45-3 | 40-29 Reference Data List Update - Item Update (golden definition) - Rejected by DS | 40-29 Reference Data List Update - Item Update (golden definition) - Rejected by DS | Passed | kassaam4 | 2018-11-22 | 7:24:45 PM | Approved
2 | OQ | 103 | Run_11-22_19-26-1 | 40-31 Reference Data List Update - Item Update (golden definition) - Accepted by DS & SDS | 40-31 Reference Data List Update - Item Update (golden definition) - Accepted by DS & SDS | Passed | kassaam4 | 2018-11-22 | 8:01:25 PM | Approved
2 | OQ | 104 | Run_11-22_20-14-56 | 40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS | 40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS | Passed | kassaam4 | 2018-11-22 | 9:04:29 PM | Approved
3 | IQ | 105 | Run_11-26_19-38-58 | SSL IQ | SSL IQ | Passed | beundor1 | 2018-11-26 | 8:46:56 PM | Approved | This was a platform level configruation
3 | IQ | 106 | Run_11-27_20-56-29 | GDD - Web IQ | GDD - Web IQ | Passed | beundor1 | 2018-11-27 | 9:31:20 PM | Approved | Changes requested to the COTS product by business users (identified during informal testing)