## Defect Summary
Count of Defect ID | Column Labels
Row Labels | IQ | OQ | UAT | Grand Total
Assigned |  | 1 |  | 1
Closed |  | 24 |  | 24
New | 11 | 2 | 15 | 28
Grand Total | 11 | 27 | 15 | 53

## Defect Data
Actual Fix Time | Approval Applied | Approval Pending | Approval Status | Assigned To | Closed in Version | Closing Date | Defect ID | Comments | Description | Defect Type | Detected By | Detected in Cycle | Detected in Release | Detected in Version | Detected on Date | Detected on Environment | Estimated Fix Time | Modified | Planned Closing Version | Priority | Project | Rejection Reason | Reproducible | Resolution | Severity | Signatures | Subject | Summary | Target Cycle | Target Release | Test ID | Test Step | Type
|  |  | New |  |  |  | 1 |  | Test Instance: [1]Rollback IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: Rollback IQ Run: Run_10-30_15-29-51 Test Parameters: Step: Step 1 Description: Create a backup directory in the /app/ebx folder using the command in cmd: mkdir –p /app/ebx/instances/backups Expected: A directory called "backups" is created in ap/ebx/instances directory Actual: There is a documentation error in Step 1 of this test case. the target location where the backups folder is to be created is /app/ebx. [User: beundor1] Run Step[1013] : Step 1 | IQ | beundor1 |  |  |  | 2018-10-30 |  |  | 2018-10-30 19:52 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | Documentation Step Error
|  |  | New |  |  |  | 2 | The installation package come with the JDK already extract. No need to execute this step. ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD Platform IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD Platform IQ Run: Run_10-30_20-27-47 Test Parameters: <<<GDD URL>>> = http://GLCHBS-ST220267.eu.novartis.net Step: Step 3 Description: Extract jdk archive using the command in cmd: tar -xzf /app/ebx/apps/jdk-8u181-linux.tar.gz -C /app/ebx/apps Expected: jdk archive is extracted Actual: There is a documentation error in step 3 of this case. The jdk is already extracted in the installation package [User: beundor1] Run Step[1027] : Step 3 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 18:50 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | Useless step. jdk is already extract in the package
|  |  | New |  |  |  | 3 | The installation package come with the tomcat already extract. No need to execute this step. ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD Platform IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD Platform IQ Run: Run_10-30_20-27-47 Test Parameters: <<<GDD URL>>> = http://GLCHBS-ST220267.eu.novartis.net Step: Step 4 Description: Extract tomcat archive using the command in cmd: tar -xzf /app/ebx/apps/apache-tomcat-8.5.33.tar.gz -C /app/ebx/apps Expected: tomcat archive is extracted Actual: There is a documentation error in step 3 of this case. The tomcat is already extracted in the installation package [User: beundor1] Run Step[1028] : Step 4 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 18:51 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | Useless step: Tomcat is already extracted in the installation package
|  |  | New | harbni1 |  |  | 4 | There is an error in the step definition. Configuration files are locate under /app/ebx/instances/gdd/ebxServer/conf folder. So the conf folder is missing in the command description. The command execute to pass the step: cp /app/ebx/instances/gdd/ebxServer/conf/environment_template.properties /app/ebx/instances/gdd/ebxServer/conf/environment.properties Once the command is executed, there is one step missing: Edit the new environment.properties file and set the properties values. ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD Platform IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD Platform IQ Run: Run_10-30_20-27-47 Test Parameters: <<<GDD URL>>> = http://GLCHBS-ST220267.eu.novartis.net Step: Step 11 Description: Create environment.properties file from template and update the database password property using the command in cmd: cp /app/ebx/instances/gdd/ebxServer/environment_template.properties /app/ebx/instances/gdd/ebxServer/environment.properties Expected: envrionment.properties file is created with appropriate database property Actual: There is a documentation error in step 11 of this case. The environment properties file is locate in conf folder inside ebxServer folder. NB: Password must be manually set by editing the environment.properties file. [User: beundor1] Run Step[1035] : Step 11 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-11-19 16:04 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | There is a documentation error in step 11. environment_template.properties files is located at /app/ebx/instances/gdd/ebxServer/conf folder.
|  |  | New |  |  |  | 5 | The environment.properties file is generated under /app/ebx/instances/gdd/ebxServer/conf folder So the command to execute is : source /app/ebx/instances/gdd/ebxServer/conf/environment.properties and the expected result : The environments properties are loaded. ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD Platform IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD Platform IQ Run: Run_10-30_20-27-47 Test Parameters: <<<GDD URL>>> = http://GLCHBS-ST220267.eu.novartis.net Step: Step 12 Description: Load the environment.properties file using the command in cmd: source /app/ebx/instances/gdd/ebxServer/environment.properties Expected: environment.properties file is loaded in directory /app/ebx/instances/gdd/ebxServer/ Actual: environment.properties file is loaded [User: beundor1] Run Step[1036] : Step 12 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 18:57 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | There is documentation error in step 12. environment.properties files is located at /app/ebx/instances/gdd/ebxServer/conf
|  |  | New |  |  |  | 6 | There is one step missing : Set the app folder permissions to 754. chmod -R 754 /app/ebx/apps ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD Platform IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD Platform IQ Run: Run_10-30_20-27-47 Test Parameters: <<<GDD URL>>> = http://GLCHBS-ST220267.eu.novartis.net Step: Step 14 Description: Start the application using the command in cmd: cd /app/ebx/instances/gdd ./start.sh Expected: application starts Actual: application starts [User: beundor1] Run Step[1038] : Step 14 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 18:59 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | The rights of the /app/ebx/apps folder should be set to 754 before.
|  |  | New |  |  |  | 7 | The delivery package is extract in a work directory. see defect n° 10. So the cmmand here become : chmod -R 774 /app/ebx/delivery/work ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD - Web IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD - Web IQ Run: Run_10-31_15-5-51 Test Parameters: <<<EBX URL>>> = http://GLCHBS-ST220267.eu.novartis.net:8080 Step: Step 3 Description: Change the rights of the extracted files to 774 using the command in cmd: chmod 774 novartis-gdd-<environment>-<timestamp> Expected: Rights are changed Actual: Rights are changed [User: beundor1] Run Step[1052] : Step 3 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 19:21 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | Files are extracted in the root of delivery folder
|  |  | New |  |  |  | 8 | The delivery package is extracted inside the /app/ebx/delivery/work folder. The command to execute in this step is: sh /app/ebx/delivery/work/deploy.sh ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD - Web IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD - Web IQ Run: Run_10-31_15-5-51 Test Parameters: <<<EBX URL>>> = http://GLCHBS-ST220267.eu.novartis.net:8080 Step: Step 4 Description: Run the the deploy.sh script as ebxuser using the command in cmd: cd novartis-gdd-<environment>-<timestamp> && ./deploy.sh Expected: Application is started Actual: Application is started [User: beundor1] Run Step[1053] : Step 4 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 19:26 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | Delivery files are extracted in the root of the delivery folder.
|  |  | New |  |  |  | 9 | The delivery package is extracted inside the /app/ebx/delivery/work folder. the command to execute in this step is: cd /app/ebx/delivery && rm -r work ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD - Web IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD - Web IQ Run: Run_10-31_15-5-51 Test Parameters: <<<EBX URL>>> = http://GLCHBS-ST220267.eu.novartis.net:8080 Step: Step 5 Description: Delete the tmp folder after the application has started using the command in cmd: rm -r novartis-gdd-<environment>-<timestamp> Expected: tmp folder is deleted Actual: Delivery extracted files are deleted [User: beundor1] Run Step[1054] : Step 5 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 19:28 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | Delivery files are extracted at the root of the delivery folder. They have been remove one by one.
|  |  | New |  |  |  | 10 | The delivery package is extracted at the root of delivery folder. One step missing before the step 2: Create a tmp work directory mkdir -p /app/ebx/delivery/work and then extract the delivery package inside the work directory. tar -xzf /app/ebx/delivery/novartis-gdd-<<env>>-<<timestamp>>.tar.gz -C /app/ebx/delivery/work ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | Test Instance: [1]GDD - Web IQ Test Set: GDD_MDM_Release0_IQ_TestSet_30Oct2018 Test: GDD - Web IQ Run: Run_10-31_15-5-51 Test Parameters: <<<EBX URL>>> = http://GLCHBS-ST220267.eu.novartis.net:8080 Run[4] : Run_10-31_15-5-51 | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 19:24 |  |  |  |  | Y |  |  |  | 30-Installation Qualification | The package are extracted at the root of delivery folder
|  |  | New |  |  |  | 11 | Missing step execution detail: 1. copy the cetificate to the /tmp folder 2.import the certificate to the default java keystore /app/ebx/apps/jdk/bin/keytool -import -alias ldap -keystore /app/ebx/apps/jdk/jre/lib/security/cacerts -file /tmp/<certificate.pem> ________________________________________ Orliac BEUNDA <beundor1>, 10/31/2018: | LDAP certifaicate installation step is missing | IQ | beundor1 |  |  |  | 2018-10-31 |  |  | 2018-10-31 19:18 |  |  |  |  | Y |  |  |  |  | LDAP certifaicate installation step is missing
24 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 12 | Root cause : Data is not in read-only acess Impact: Data can be modified Solution: It is not a defect . Data is in read-only mode outside the workflow and in write mode inside the workflow ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-01 Access Rights check Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-01 Access Rights check Run: Run_11-5_19-33-33 Test Parameters: <<<gdd url>>> = "" Step: Step 7 Description: Click on the Reference Data List option on the left navigation menu Expected: Reference data lists is dsiplayed in read only mode (user can't modify anything) Actual: Reference Data Lists ARE available for Update [User: schulmig] Run Step[1065] : Step 7 | OQ | schulmig |  |  |  | 2018-11-06 |  |  | 2018-11-29 11:55 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:54:34 Meaning: Closed | 40-Functional Testing | Documented result to be read only. Actual result - update available
24 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 13 | Root cause : this is a misunderstanding. User logs in in step 1 as Senior Data Steward and in step 4 , he logs out and logs in as a Data Steward Impact: Solution : it is not a defect . ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-02 BR WF-18 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-02 BR WF-18 Run: Run_11-6_20-9-18 Test Parameters: <<<gdd url>>> = "" Step: Step 4 Description: Logout and login as Data Steward n°1 Expected: The user is logged as Data Steward and GDD perspective opens Actual: Logging Out as Senior Data Steward, NOT as Data Steward (See Step 1) [User: schulmig] Run Step[1104] : Step 4 | OQ | schulmig |  |  |  | 2018-11-06 |  |  | 2018-11-29 11:55 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:54:57 Meaning: Closed | 40-Functional Testing | This scenarios has user log in as Senior Data Steward, but log out as Data Steward. This is obviously a typing error. Expected result should be corrected. The outcome makes sense
23 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 14 | Root cause :Order of fields in data dictionary is different from the one in UI Impact: Order is not correct Solution : it has been corrected in data dictionary and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-03 Data Model check Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-03 Data Model check Run: Run_11-7_14-27-12 Test Parameters: <<<gdd url>>> = "" Step: Step 10 Description: Check order of fields in the gird Expected: Order must be same as defined in the attached data dictionnary (attached to test case) Actual: Spreadsheet lists fields Id then Code. UI shows Code then ID. The rest match up Run Step[1138] : Step 10 | OQ | schulmig |  |  |  | 2018-11-07 |  |  | 2018-11-29 11:55 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:55:19 Meaning: Closed | 40-Functional Testing | Field Sequence does not match the documented expected results
23 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 15 | Root cause : Optional fields are tested separatly in OQs dedicated to Business rules . Here, the aim is to verify as a technical administrator that all the fileds (including optional and mandatories fields) that should be present are really present. We also verify that restrictions , fields names and order are correct. Impact:There is no impact Solution : This is not a defect but a misunderstanding ________________________________________ Amel Kassa <kassaam4>, 11/21/2018: | Test Instance: [1]40-03 Data Model check Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-03 Data Model check Run: Run_11-7_14-27-12 Test Parameters: <<<gdd url>>> = "" Step: Step 12 Description: Repeat from step 5 onward for each table (items, Applications, items permissions, list permissions) Expected: expected results should be same as the ones mentioned in each step Actual: All Front page Screens Match sequence expected (Items, Applications, Item Permissions, List Permissions) Application, List Permissions, and Item Permissions match the detailed view. Items does not match due to 'conditional' fields. Test case does not establish the pre-requisite to see the conditional fields. The needed data will be tested later. [User: schulmig] Run Step[1140] : Step 12 | OQ | schulmig |  |  |  | 2018-11-07 |  |  | 2018-11-29 11:56 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:55:38 Meaning: Closed | 40-Functional Testing | Fields that are optional based upon a specific list are not showing up as those lists have not yet been introduced into the system and is not mentioned as a pre-requisite for this scenario. There is a high degree of confidence that there is no issue here,
23 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 16 | Root cause : no duplicate was found Impact: manage view should appear Solution : it is not a defect , it is a misunderstanding. It was tested and it works well An existing label among exiting items was used and put in "label" field , then , after saving , the manage duplicate view appears and allows user to choose between creating a golden (confirm) ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-04 BR WF-22 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-04 BR WF-22 Run: Run_11-7_18-53-17 Test Parameters: <<<gdd url>>> = "" Step: Step 6 Description: Click on "Confirm" in the manage view Expected: The user confirms his choice to create a golden (duplicate) for Item Actual: No Duplicate was identified. Reference List moved along into the workflow Run Step[1147] : Step 6 | OQ | schulmig |  |  |  | 2018-11-07 |  |  | 2018-11-29 11:56 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:56:02 Meaning: Closed | 40-Functional Testing | A duplicate LABEL was entered. Duplicate management was not triggered
22 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 17 | Root cause : it is a misunderstanding Code should not contain any whitespace at the begining before the entered value Impact: Primary key as code should not contain whitespace Solution : it is not a defect , any error message is expected ad EBX removes automatically whitespace when user is saving record ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-16 Reference Data List Creation - Rejected by SDS Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-16 Reference Data List Creation - Rejected by SDS Run: Run_11-8_15-51-53 Test Parameters: <<<gdd url>>> = "" Step: Step 5 Description: Click on "Save" Expected: Changes are saved Actual: Upon clicking Save I was expecting an error message as CODE is not supposed to accept white space. I did not get that error message, but it seems the list has been saved Run Step[1292] : Step 5 | OQ | schulmig |  |  |  | 2018-11-08 |  |  | 2018-11-29 11:56 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:56:20 Meaning: Closed | 40-Functional Testing | Data Quality check on Code field is not being performed as expected
22 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 18 | Root cause : Historization was missing for Items entities Impact :Events are not tracked in "Historization" Solution: it has been corrected in the Code and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-61 Historization Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-61 Historization Run: Run_11-8_15-50-17 Test Parameters: <<<gdd url>>> = http://glchbs-st220267.eu.novartis.net:8080/ebx/ Step: Step 15 Description: Open a record to display details Expected: Details can be shown Actual: Fail Run Step[1425] : Step 15 | OQ | roberfr5 |  |  |  | 2018-11-08 |  |  | 2018-11-29 11:57 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:56:34 Meaning: Closed | 40-Functional Testing | History does not show on items
22 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 19 | Root cause : "list of suspicious" section appears Impact: it does not work correctly as there is no duplicate, this section should not be there Solution: it has been corrected in Code and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-41 BR WF-10 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-41 BR WF-10 Run: Run_11-8_14-17-44 Test Parameters: <<<GDD Dev URL>>> = "" <<<gdd url>>> = "" Step: Step 33 Description: Click on "Start work item" Expected: The workflow item is available Actual: The wokitem is available List of suspicious should not be present as I have not created a duplicate Run Step[1328] : Step 33 | OQ | kassaam4 |  |  |  | 2018-11-08 |  |  | 2018-11-29 11:58 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:57:38 Meaning: Closed | 40-Functional Testing | List of suspicious section is present whereas it should not be there
22 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 20 | Root cause : Permissions are not created through Reference Data List Creation Workflow Impact: Permissions are not available to be updated during the Reference Data List Creation Workflow Solution: It has been corrected in Code and it will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-15 Reference Data List Creation - Accepted by SDS & SME Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-15 Reference Data List Creation - Accepted by SDS & SME Run: Run_11-8_17-4-5 Test Parameters: <<<gdd url>>> = "" Step: Step 6 Description: Try to add or udpate permissions in "Application permissions" tab Expected: During process it is possible to add or udpate permissions in "Application permissions" tab Actual: Clicking on Application Permission tab, message displays that this is explicitly NOT possible to add/update now Run Step[1458] : Step 6 | OQ | schulmig |  |  |  | 2018-11-08 |  |  | 2018-11-29 11:58 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:57:56 Meaning: Closed | 40-Functional Testing | Result is opposite to documented - Cannot Add/Update
22 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 21 | Root cause :rejection mail was not received by requestor Impact: Requestor is not notified for rejection Solution : it has been corrected in the Code and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-20 Reference Data List Creation - Golden definition - Rejected by SDS Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-20 Reference Data List Creation - Golden definition - Rejected by SDS Run: Run_11-8_17-36-16 Test Parameters: <<<gdd url>>> = "" Step: Step 16 Description: The workflow item has been rejected by the Senior Data Steward n°2 (different from requestor). Verify that the SDS 1 (which is the requestor) is notified by email of the decision Expected: Senior Data Steward n°1 has received an email notification from MDM. Actual: No email received for the rejection Run Step[1516] : Step 16 | OQ | schulmig |  |  |  | 2018-11-08 |  |  | 2018-11-29 11:58 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:58:18 Meaning: Closed | 40-Functional Testing | Other notification emails arriving...this one of rejection did not
21 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 22 | Root cause : Permissions are not created through Reference Data List Creation Workflow Impact: Permissions are not available to be updated during the Reference Data List Creation Workflow Solution: It has been corrected in Code and it will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-46 BR GDD 04 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-46 BR GDD 04 Run: Run_11-9_12-16-39 Test Parameters: <<<gdd url>>> = "" Step: Step 10 Description: Go on "Application permisions" tab Expected: Permissions are available for RD List Actual: Permissions are not available for RD List Run Step[1683] : Step 10 | OQ | kassaam4 |  |  |  | 2018-11-09 |  |  | 2018-11-29 11:59 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:58:59 Meaning: Closed | 40-Functional Testing | Permisisons have not been created during the workflow
17 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 23 | Root cause : "list of suspicious" section appears Impact: it does not work correctly as there is no duplicate, this section should not be there Solution: it has been corrected in Code and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-53 BR GDD-12 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-53 BR GDD-12 Run: Run_11-13_14-38-26 Test Parameters: <<<gdd url>>> = "" Step: Step 10 Description: To review the workflow, click on "Inbox", you should have a red flag on your Inbox. Expected: The workflow item is available in MDM Inbox, the DS 2 can do a review Actual: The workflow item is available in MDM Inbox, the DS 2 can do a review [User: kassaam4] Run Step[2523] : Step 10 | OQ | kassaam4 |  |  |  | 2018-11-13 |  |  | 2018-11-29 11:59 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:59:22 Meaning: Closed | 40-Functional Testing | List of suspicious section is available whereas they are no duplicates
17 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 24 | Root cause :Script task error Impact: Workflow can not be pursued Solution : it has been corrected in the Code and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-53 BR GDD-12 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-53 BR GDD-12 Run: Run_11-13_14-38-26 Test Parameters: <<<gdd url>>> = "" Step: Step 13 Description: Click on "Ok" to confirm the approval Expected: The approval is confirmed Actual: The approval is confirmed [User: kassaam4] Run Step[2526] : Step 13 | OQ | kassaam4 |  |  |  | 2018-11-13 |  |  | 2018-11-29 12:00 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 11:59:51 Meaning: Closed | 40-Functional Testing | Fail to run the script task : blocked at apply business decision step
17 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 25 | Root cause : the QO script contains error Impact: the error message was not good Solution: Script error has been corrected ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-58 BR GDD 17 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-58 BR GDD 17 Run: Run_11-13_17-25-15 Test Parameters: <<<gdd url>>> = "" Step: Step 15 Description: Check that there is no error message Expected: An error message is not displayed: Actual: There is an error message when the label size is more than 80 characters Run Step[2725] : Step 15 | OQ | kassaam4 |  |  |  | 2018-11-13 |  |  | 2018-11-29 12:00 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:00:28 Meaning: Closed | 40-Functional Testing | Documentation to be updates : There is an error message when the label size is more than 80 characters
17 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 26 | Root cause :error message disappears when user user saves record Impact: error message is displayed and disappears when user is saving record Solution: It is a misunderstanding , record needs to be saved in order to make disapear error message ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-57 BR GDD 16 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-57 BR GDD 16 Run: Run_11-13_17-36-54 Test Parameters: <<<gdd url>>> = "" Step: Step 12 Description: Check that there is no error message Expected: The error message is not displayed Actual: The error message is displayed telling us that this field is mandatory But this field has be filled . User needs to save in order to make this warning disappear Run Step[2738] : Step 12 | OQ | kassaam4 |  |  |  | 2018-11-13 |  |  | 2018-11-29 12:01 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:00:58 Meaning: Closed | 40-Functional Testing | Mandatory warning whereas field is filled
16 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 27 | Root cause : the QO script contains error Impact: the steps were not good Solution: Script error has been corrected ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-07 BR WF-14 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-07 BR WF-14 Run: Run_11-13_19-51-51 Test Parameters: <<<gdd url>>> = "" Step: Step 15 Description: Senior Data Steward 2 waits one week as the notifications for pending workflows are on weekly basis Expected: Check that you have received as SME a mail notification containing the list of pending workflow to approve Actual: The SME has to wait one week Run Step[2637] : Step 15 | OQ | kassaam4 |  |  |  | 2018-11-14 |  |  | 2018-11-29 12:01 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:01:18 Meaning: Closed | 40-Functional Testing | steps are not correct : OQ problem
16 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 28 | Root cause :Script task error Impact: Workflow can not be pursued Solution : it has been corrected in the Code and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS Run: Run_11-12_16-37-9 Test Parameters: <<<gdd url>>> = "" Step: Step 21 Description: Check that SDS has received an email notification from MDM to review this request. Expected: SDS has received an email notification from MDM Actual: SDS has received an email notification from MDM Run Step[2134] : Step 21 | OQ | kassaam4 |  |  |  | 2018-11-14 |  |  | 2018-11-29 12:02 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:01:39 Meaning: Closed | 40-Functional Testing | problem of script task in the WF - not received by SDS
16 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 29 | Root cause :Script task error Impact: Workflow can not be pursued Solution : it has been corrected in the Code and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/20/2018: | Test Instance: [1]40-31 Reference Data List Update - Item Update (golden definition) - Accepted by DS & SDS Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-31 Reference Data List Update - Item Update (golden definition) - Accepted by DS & SDS Run: Run_11-9_20-56-53 Test Parameters: <<<gdd url>>> = "" Step: Step 21 Description: Check that SDS has received an email notification from MDM to review this request. Expected: SDS has received an email notification from MDM Actual: SDS has not received an email notification from MDM Run Step[2102] : Step 21 | OQ | kassaam4 |  |  |  | 2018-11-14 |  |  | 2018-11-29 12:02 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:02:02 Meaning: Closed | 40-Functional Testing | script task error
16 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 30 | Root cause : Data Steward 1 has not received rejection notification Impact: Requestor is not notificated about rejection Solution: It has been corrected in Code and will be tested in Round 2 ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-36 Reference Data List Update - Item Update - Rejected by DS Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-36 Reference Data List Update - Item Update - Rejected by DS Run: Run_11-12_17-13-52 Test Parameters: <<<gdd url>>> = "" Step: Step 16 Description: The workflow item has been rejected by the Data Steward n°2 (different from requestor). Verify that the DS 1 (which is the requestor) is notified by email of the decision Expected: Data Steward n°1 has received an email notification from MDM. Actual: Data Steward n°1 has not received an email notification from MDM. Run Step[2171] : Step 16 | OQ | kassaam4 |  |  |  | 2018-11-14 |  |  | 2018-11-29 12:02 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:02:23 Meaning: Closed | 40-Functional Testing | DS1 has not received email for rejection
16 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 31 | Root cause : for wrong password , data was present Impact: Data is available even if the password is wrong Solution: It is not a defect , it just needs to delete history before executing tests ________________________________________ Amel Kassa <kassaam4>, 11/19/2018: | Test Instance: [1]40-66 System Connection to MDM through API GW Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-66 System Connection to MDM through API GW Run: Run_11-14_15-37-6 Test Parameters: <<<GDD URL>>> = "" <<<KeyID>>> = "" <<<Select Reference Item>>> = "" <<<UserID>>> = "" Step: Step 7 Description: Repeat Step 2 to Step 6, and provide wrong password at final step Expected: An error is displayed Actual: There are no error , data is displayed Run Step[2765] : Step 7 | OQ | kassaam4 |  |  |  | 2018-11-14 |  |  | 2018-11-29 12:03 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:02:52 Meaning: Closed | 40-Functional Testing | no error message for wrong password
10 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 32 | Root cause : Icon to click is present if the List has its status = "Published" otherwise if the List has its status = "Deleted" , there is no icon Impact: no impact Solution : this is not a defect , it is a misunderstanding ________________________________________ Amel Kassa <kassaam4>, 11/21/2018: | Test Instance: [1]40-32 Reference Data List Update - Item Update (golden definition) - Record locked Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-32 Reference Data List Update - Item Update (golden definition) - Record locked Run: Run_11-9_19-24-27 Test Parameters: <<<gdd url>>> = "" Run[50] : Run_11-9_19-24-27 | OQ | schulmig |  |  |  | 2018-11-20 |  |  | 2018-11-29 12:03 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:03:29 Meaning: Closed | 40-Functional Testing | Icon to click was not present
10 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 33 | Root cause: there is no confirmation screen Impact: there is no impact Solution: it is a script error , it has been corrected in the OQ ________________________________________ Amel Kassa <kassaam4>, 11/21/2018: | Test Instance: [1]40-38 Reference Data List Update - Update Request - Accepted by SDS & Rejected by SME Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-38 Reference Data List Update - Update Request - Accepted by SDS & Rejected by SME Run: Run_11-12_21-35-1 Test Parameters: <<<gdd url>>> = "" Run[64] : Run_11-12_21-35-1 | OQ | schulmig |  |  |  | 2018-11-20 |  |  | 2018-11-29 12:05 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:04:39 Meaning: Closed | 40-Functional Testing | No Confirmation screen
10 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 34 | Root cause : this business rule has been removed Impact:code can not be sensitive Solution: it has been corrected in the code (new business rule has been added providing same result) and will be tested in round 2 ________________________________________ Amel Kassa <kassaam4>, 11/21/2018: | Test Instance: [1]40-55 BR GDD 14 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-55 BR GDD 14 Run: Run_11-13_16-53-13 Test Parameters: <<<gdd url>>> = "" Run[74] : Run_11-13_16-53-13 | OQ | schulmig |  |  |  | 2018-11-20 |  |  | 2018-11-29 12:05 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:05:27 Meaning: Closed | 40-Functional Testing | Referenced Error message not shown
|  |  | Assigned | harbni1 |  |  | 35 | Root cause : "Parent" field is optional , all level (except SOC) can have parent OQs corrections have just been delivered , IQs have been sent to approval and we are going to begin OQ execution for round 2 We can not modify "Parent" field to be mandatory for all levels except SOC Impact:No impact Solution: It will be delivered later ________________________________________ Amel Kassa <kassaam4>, 11/21/2018: | Test Instance: [1]40-59 BR GDD 18 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-59 BR GDD 18 Run: Run_11-13_19-31-26 Test Parameters: <<<gdd url>>> = "" Run[79] : Run_11-13_19-31-26 | OQ | schulmig |  |  |  | 2018-11-20 |  |  | 2018-11-29 09:39 |  |  |  |  | Y |  |  |  | 40-Functional Testing | Conditional Mandatory Attribute not handled
|  |  | New | harbni1 |  |  | 36 | Root cause : workitem label is not correct it should be "Manage duplicate" and not "Correct errors" Impact: workitem label is not correct Solution: it is an OQ script error , it will be corrected ________________________________________ Amel Kassa <kassaam4>, 11/23/2018: | Test Instance: [1]40-20 Reference Data List Creation - Golden definition - Rejected by SDS Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-20 Reference Data List Creation - Golden definition - Rejected by SDS Run: Run_11-21_18-59-24 Test Parameters: <<<gdd url>>> = "" Step: Step 21 Description: Click on "Start Work Item" The label of this Work Item is "Correct errors" Expected: The workflow item is available Actual: Label of this Work Item is Manage Duplicate Run Step[2881] : Step 21 | OQ | schulmig |  |  |  | 2018-11-21 |  |  | 2018-11-23 12:28 |  |  |  |  | Y |  |  |  | 40-Functional Testing | Work Item Label does not match Script
8 | Defect Manager | Reviewer 1 | Closed | harbni1 |  | 2018-11-29 | 37 | Root cause : error message is displayed but import was successful Impact: error message should not be displayed Solution: it can not be corrected as it is part of Import excel tool ________________________________________ Amel Kassa <kassaam4>, 11/23/2018: | Test Instance: [1]40-65 Data Transfer to MDM Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-65 Data Transfer to MDM Run: Run_11-22_14-42-50 Test Parameters: <<<GDD URL>>> = "" Step: Step 7 Description: Click on Import at the bottom right Expected: a summary page is displayed on how many records are inserted, updated, deleted or not chnaged Actual: as expected [User: kassaam4] Run Step[3095] : Step 7 | OQ | kassaam4 |  |  |  | 2018-11-22 |  |  | 2018-11-29 12:07 |  |  |  |  | Y |  |  | Signed by : Nidal Harb (harbni1) on 2018-11-29 12:06:43 Meaning: Closed | 40-Functional Testing | "Parent " field can not be empty for Import
|  |  | New | harbni1 |  |  | 38 | Root cause : OQ script does not say to correct Code Impact: steps are not correct Solution: it is an OQ script error , it will be corrected ________________________________________ Amel Kassa <kassaam4>, 11/23/2018: | Test Instance: [1]40-55 BR GDD 14 Test Set: GDD_MDM_Release0_OQ_TestSet_30Oct2018 Test: 40-55 BR GDD 14 Run: Run_11-22_15-32-41 Test Parameters: <<<gdd url>>> = "" Step: Step 9 Description: Click on "Send to Review" Expected: The creation request is sent to SDS Team Actual: issue with the script the script does not say to correct the data and the new BR disable the Send Button [User: roberfr5] Run Step[3217] : Step 9 | OQ | kassaam4 |  |  |  | 2018-11-23 |  |  | 2018-11-23 12:29 |  |  |  |  | Y |  |  |  | 40-Functional Testing | OQ script error : script deos not say to correct data
|  |  | New |  |  |  | 39 |  | Test Instance: [1]5.0 External Source Hierarchy List Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 5.0 External Source Hierarchy List Run: Run_11-30_13-21-42 Test Parameters: Step: Step 1 Description: Login to EBX as SDS1 Import Meddra Data Submit for Review Login to EBX as SDS2 Approve Meddra Data Login to EBX as SME Approve Meddra Data View Hierarchy relationship of Meddra Data Expected: See that the hierarchy has been created Actual: Not possible to create MEDDRA list in EBX5 becuase the code MEDDRA is already existing. The MEDDRA specific business rules are linked to the text code, thus is not possible to test this type of list if the code is already existing. Run Step[3338] : Step 1 | UAT | castrad9 |  |  |  | 2018-11-30 |  |  | 2018-11-30 13:30 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Not possible to create MEDDRA list - business rules linked to text code
|  |  | New |  |  |  | 40 |  | Test Instance: [1]2.0 - Verify Entity Creation Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 2.0 - Verify Entity Creation Run: Run_11-30_14-6-13 Test Parameters: Step: Step 1 Description: Login to EBX as SDS1 Create Reference List While Entering Code (attribute) include a ' ' <SPACE Character> Save and Submit For Review Expected: System should present an Error Message requiring a correction to Code which may not contain a space character Actual: Didn't get an error when having a space in the code I cant see the description of the workflow in the list of "Active Workflows" Run Step[3339] : Step 1 | UAT | castrad9 |  |  |  | 2018-11-30 |  |  | 2018-11-30 14:13 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Worflow description is not visible in the list of active workflows
|  |  | New |  |  |  | 41 |  | Test Instance: [1]2.0 - Verify Entity Creation Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 2.0 - Verify Entity Creation Run: Run_11-30_14-6-13 Test Parameters: Step: Step 1 Description: Login to EBX as SDS1 Create Reference List While Entering Code (attribute) include a ' ' <SPACE Character> Save and Submit For Review Expected: System should present an Error Message requiring a correction to Code which may not contain a space character Actual: Didn't get an error when having a space in the code I cant see the description of the workflow in the list of "Active Workflows" Run Step[3339] : Step 1 | UAT | castrad9 |  |  |  | 2018-11-30 |  |  | 2018-11-30 14:13 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | No error message when creating a code with spaces in between.
|  |  | New |  |  |  | 42 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 1 Description: Login to EBX5 as SDS1 Use Search Bar to find the List entered in Create List Test Scenario Expected: Search should filter the results set Actual: With the search term "UAT" the newly created list "TEST UAT 001", but also other list that doesn't meet the search criteria. See attachment. Run Step[3401] : Step 1 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 05:25 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Search by text provides reuslt not meeting search criteria
|  |  | New |  |  |  | 43 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 2 Description: Make an Application be a subscriber to this list* Change the Label to start with the word 'TEST' Save and Submit for Review Login to EBX5 as SDS2 Approve Label change Submit for Publishing Login to EBX5 as SME Approve Label Change on the list go to API URL See List Label has been modified Expected: See revision Actual: Changed label of existing "TEST UAT 001" to "TEST2 UAT 001" Add permissions to Horizon, Workbench and Impact Run Step[3402] : Step 2 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 05:50 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Not possible to see all the new applications in the summary of changes for approver
|  |  | New |  |  |  | 44 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 2 Description: Make an Application be a subscriber to this list* Change the Label to start with the word 'TEST' Save and Submit for Review Login to EBX5 as SDS2 Approve Label change Submit for Publishing Login to EBX5 as SME Approve Label Change on the list go to API URL See List Label has been modified Expected: See revision Actual: Changed label of existing "TEST UAT 001" to "TEST2 UAT 001" Add permissions to Horizon, Workbench and Impact [User: castrad9] Run Step[3402] : Step 2 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 05:54 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | System allow to set an application to active without start date.
|  |  | New |  |  |  | 45 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 2 Description: Make an Application be a subscriber to this list* Change the Label to start with the word 'TEST' Save and Submit for Review Login to EBX5 as SDS2 Approve Label change Submit for Publishing Login to EBX5 as SME Approve Label Change on the list go to API URL See List Label has been modified Expected: See revision Actual: Changed label of existing "TEST UAT 001" to "TEST2 UAT 001" Add permissions to Horizon, Workbench and Impact [User: castrad9] Run Step[3402] : Step 2 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 05:56 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Not possible to search a list by permissions
|  |  | New |  |  |  | 46 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 3 Description: Login to EBX5 as SDS1 Select the same list and go to details Add new item to the list Delete another item from the list Save and submit for Review Login to EBX5 as SDS2 Approve changes for the list Login to EBX5 as SME Approve Chnages to Publish Got to API URL to get the list Note that the new item is present The deleted one is not Expected: The changes (Add and Delete) should be properly reflected by its existence and that the other is not Actual: When ading a new item to an stadnard list, the fields "Meddra Code Type" and Abbreviation" shoudl not be seen. Run Step[3403] : Step 3 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 06:02 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | When ading a new item to an stadnard list, the fields "Meddra Code Type" and Abbreviation" shoudl not be seen.
|  |  | New |  |  |  | 47 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 3 Description: Login to EBX5 as SDS1 Select the same list and go to details Add new item to the list Delete another item from the list Save and submit for Review Login to EBX5 as SDS2 Approve changes for the list Login to EBX5 as SME Approve Chnages to Publish Got to API URL to get the list Note that the new item is present The deleted one is not Expected: The changes (Add and Delete) should be properly reflected by its existence and that the other is not Actual: When ading a new item to an stadnard list, the fields "Meddra Code Type" and Abbreviation" shoudl not be seen. Run Step[3403] : Step 3 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 06:17 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | System allows to create a code with spaces
|  |  | New |  |  |  | 48 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 3 Description: Login to EBX5 as SDS1 Select the same list and go to details Add new item to the list Delete another item from the list Save and submit for Review Login to EBX5 as SDS2 Approve changes for the list Login to EBX5 as SME Approve Chnages to Publish Got to API URL to get the list Note that the new item is present The deleted one is not Expected: The changes (Add and Delete) should be properly reflected by its existence and that the other is not Actual: When ading a new item to an stadnard list, the fields "Meddra Code Type" and Abbreviation" shoudl not be seen. SDS didn't received the request for review. Only DS. Run Step[3403] : Step 3 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 06:20 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | SDS can't do the review of an Item Update
|  |  | New |  |  |  | 49 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 3 Description: Login to EBX5 as SDS1 Select the same list and go to details Add new item to the list Delete another item from the list Save and submit for Review Login to EBX5 as SDS2 Approve changes for the list Login to EBX5 as SME Approve Chnages to Publish Got to API URL to get the list Note that the new item is present The deleted one is not Expected: The changes (Add and Delete) should be properly reflected by its existence and that the other is not Actual: When ading a new item to an stadnard list, the fields "Meddra Code Type" and Abbreviation" shoudl not be seen. SDS didn't received the request for review. Only DS. DS couldn't see the compare of changes when doing review - fatal error. Run Step[3403] : Step 3 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 06:22 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | DS couldn't see the compare of changes when doing review - fatal error.
|  |  | New |  |  |  | 50 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 3 Description: Login to EBX5 as SDS1 Select the same list and go to details Add new item to the list Delete another item from the list Save and submit for Review Login to EBX5 as SDS2 Approve changes for the list Login to EBX5 as SME Approve Chnages to Publish Got to API URL to get the list Note that the new item is present The deleted one is not Expected: The changes (Add and Delete) should be properly reflected by its existence and that the other is not Actual: When ading a new item to an stadnard list, the fields "Meddra Code Type" and Abbreviation" shoudl not be seen. SDS didn't received the request for review. Only DS. DS couldn't see the compare of changes when doing review - fatal error occurred. Still possible to approve the request, but when arrives to last approver it again has an error and ca'n't see anything. Approval still possible. Data is published but with wrong dates. Run Step[3403] : Step 3 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 06:34 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Data is published with wrong dates
|  |  | New |  |  |  | 51 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]3.0 Modify List-Item Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 3.0 Modify List-Item Run: Run_12-3_5-16-54 Test Parameters: Step: Step 4 Description: Go to email for application - See Change notification Expected: Get the email that new reference data is available Actual: Did not received email Run Step[3404] : Step 4 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 06:40 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Email is not received
|  |  | New |  |  |  | 52 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]4.0 - Match Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 4.0 - Match Run: Run_12-3_6-42-20 Test Parameters: Step: Step 1 Description: Login to EBX5 as SDS1 Create a Reference List (Use Data to trigger Match Error ) Save and submit for Review Notice results of 'Match' Expected: Capture screen with warning of potential duplicate Actual: Abel to trigger the creation of a list with the same name as "TEST UAT 001", but without spaces "TESTUAT001" and there was not duplicate check warning. Run Step[3405] : Step 1 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 06:58 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Warning for potential duplicates not triggered
|  |  | New |  |  |  | 53 | Defect Analysis: Root Cause: <&lt What is the reason for the issue occurred >&gt System Impact: <&lt Does it impact the system? (Yes/No) provide justification >&gt Corrective Action: <&lt What is the corrective action to rectify the issue occurred? >&gt Test Impact Assessment (Re-Testing): <&lt Does this issue require a full/partial re-execution? (Yes/No) provide justification >&gt Preventative Action: <&lt What measures will be performed to avoid this issue in future? >&gt Resolution Status: <&lt Was the corrective action (re-testing) & preventative action performed? What is the status? >&gt | Test Instance: [1]1.0 - MDM Import Data Test Set: GDD_MDM_Release0_UAT_TestSet_30Oct2018 Test: 1.0 - MDM Import Data Run: Run_12-3_18-0-42 Test Parameters: Step: Step 4 Description: Import Reference List Submit for Review Expected: Actual: It is possible to import a file, but when is sent to review, nothing is visible. If a click "Compare changes" I get an error I need to reject de flow, so not possible to continue. SDS shoudl be able to trigger and review item importsm but currently only DS role can review. Run Step[3413] : Step 4 | UAT | castrad9 |  |  |  | 2018-12-03 |  |  | 2018-12-03 18:24 |  |  |  |  | Y |  |  |  | 50-User Acceptance Testing | Import file is not visible