## Test Summary (Release 0)
Test Type | Test: Test Name | Test: Overall Status | Execuion Round | Run ID | Run Name | Run: Execution Status | Run: Exec Date | Approval Status | Comment
IQ | GDD - Web IQ | Passed | 1 | 4 | Run_10-31_15-5-51 | Passed | 2018-10-31 | Approved | N/A
|  |  | 2 | 90 | Run_11-21_14-9-0 | Passed | 2018-11-21 | Approved | N/A
|  |  | 3 | 106 | Run_11-27_20-56-29 | Passed | 2018-11-27 | Approved | Changes requested to the COTS product by business users (identified during informal testing)
|  |  | 4 |  | Run_12-5_14-52-34 | Passed | 2018-12-05 | Approved | Implementation of defect fixes raised during UAT Testing
IQ | GDD Platform IQ | Passed | 1 | 3 | Run_10-30_20-27-47 | Passed | 2018-10-31 | Approved | MDM Platform installation
IQ | Rollback IQ | Passed | 1 | 2 | Run_10-30_15-29-51 | Passed | 2018-10-30 | Approved | The IQ to setup the Platform components was executed informally on the QA environment instead of the Development environment. This IQ was executed in order to revert those changes.
IQ | SSL IQ | Passed | 1 | 105 | Run_11-26_19-38-58 | Passed | 2018-11-26 | Approved | This was a platform level configruation executed in later stage to address a gap in IGM Security Risk Assessment
OQ | 40-01 Access Rights check | Failed | 1 | 5 | Run_11-5_19-33-33 | Failed | 2018-11-06 | Approved | Script Error, OQ Script was modified
OQ | 40-02 BR WF-18 | Passed | 1 | 6 | Run_11-6_20-9-18 | Passed | 2018-11-09 | Approved | N/A
OQ | 40-03 Data Model check | Failed | 1 | 8 | Run_11-7_14-27-12 | Failed | 2018-11-07 | Approved | Script Error, OQ Script was modified
OQ | 40-04 BR WF-22 | Failed | 1 | 9 | Run_11-7_18-53-17 | Failed | 2018-11-07 | Approved | Script Error, OQ Script was modified
OQ | 40-05 Reference List Creation button | Passed | 1 | 10 | Run_11-7_19-33-53 | Passed | 2018-11-07 | Approved | N/A
OQ | 40-06 BR-WF 01 | Passed | 1 | 11 | Run_11-7_19-58-1 | Passed | 2018-11-07 | Approved | N/A
OQ | 40-07 BR WF-14 | Failed | 1 | 12 | Run_11-7_20-5-44 | Not Completed | 2018-11-07 | Obsolete | Run was cancelled on purpose as the tester needed a clarification
|  |  |  | 80 | Run_11-13_19-51-51 | Failed | 2018-11-13 | Approved | Script Error, OQ Script was modified
OQ | 40-08 BR WF-19 | Passed | 1 | 13 | Run_11-7_20-21-52 | Passed | 2018-11-07 | Approved | N/A
OQ | 40-09 Options to launch the deletion by SDS | Passed | 1 | 14 | Run_11-7_20-34-31 | Passed | 2018-11-07 | Approved | N/A
OQ | 40-10 Reference Data List - Deletion Request - Accepted by SDS & Rejected by SME | Passed | 1 | 15 | Run_11-7_20-55-34 | Not Completed | 2018-11-07 | Obsolete | Run was cancelled on purpose as the tester needed a clarification
|  |  |  | 82 | Run_11-13_20-40-26 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-11 Reference Data List - Deletion Request - Accepted by SDS & SME | Passed | 1 | 16 | Run_11-7_21-24-40 | Not Completed | 2018-11-07 | Obsolete | Run was cancelled on purpose as the tester needed a clarification
|  |  |  | 83 | Run_11-13_20-49-27 | Passed | 2018-11-13 | Approved | N/A
OQ | 40-12 Reference Data List - Deletion Request - Record Locked | Passed | 1 | 17 | Run_11-7_21-47-9 | Passed | 2018-11-07 | Approved | N/A
OQ | 40-13 Reference Data List - Deletion Request - Rejected by SDS | Passed | 1 | 18 | Run_11-7_21-57-27 | Not Completed | 2018-11-07 | Obsolete | Run was cancelled on purpose as the tester needed a clarification
|  |  |  | 81 | Run_11-13_20-10-4 | Failed | 2018-11-13 | Approved | Code Issues
|  |  | 2 | 94 | Run_11-21_18-25-35 | Passed | 2018-11-21 | Approved | N/A
OQ | 40-14 Reference Data List Creation - Accepted by SDS & Rejected by SME | Passed | 1 | 23 | Run_11-8_16-22-5 | Passed | 2018-11-08 | Approved | N/A
OQ | 40-15 Reference Data List Creation - Accepted by SDS & SME | Failed | 1 | 24 | Run_11-8_17-4-5 | Failed | 2018-11-08 | Approved | Script Error, OQ Script was modified
OQ | 40-16 Reference Data List Creation - Rejected by SDS | Failed | 1 | 22 | Run_11-8_15-51-53 | Failed | 2018-11-08 | Approved | Script Error, OQ Script was modified
OQ | 40-17 Reference Data List Creation - Golden definition - Accepted by SDS & SME | Passed | 1 | 29 | Run_11-8_20-47-11 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-18 Reference Data List Creation - Golden definition - Accepted by SDS & Rejected by SME | Passed | 1 | 28 | Run_11-8_19-57-1 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-19 Reference Data List Creation - Golden definition - Record locked | Passed | 1 | 27 | Run_11-8_19-5-39 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-20 Reference Data List Creation - Golden definition - Rejected by SDS | Failed | 1 | 26 | Run_11-8_17-36-16 | Failed | 2018-11-08 | Approved | Code Issues
|  |  | 2 | 95 | Run_11-21_18-59-24 | Failed | 2018-11-21 | Approved | Script Error, OQ Script was modified
OQ | 40-21 Reference Data List Creation - Pivot definition - Record Locked | Passed | 1 | 42 | Run_11-9_16-10-28 | Failed | 2018-11-09 | Obsolete | Run was cancelled on purpose as the tester needed a clarification
|  |  |  | 84 | Run_11-13_22-19-33 | Passed | 2018-11-13 | Approved | N/A
OQ | 40-22 Reference Data List Creation - Pivot definition - Rejected by SDS | Failed | 1 | 43 | Run_11-9_16-47-39 | Failed | 2018-11-09 | Approved | Script Error, OQ Script was modified
OQ | 40-23 Reference Data List Creation - Pivot defintion - Accepted by SDS & Rejected by SME | Passed | 1 | 44 | Run_11-9_17-37-0 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-24 Reference Data List Creation - Pivot defintion - Accepted by SDS & SME | Passed | 1 | 48 | Run_11-9_18-35-48 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-25 Reference Data List Update - Item Update (cancel creation) - Accepted by DS & Rejected by SDS | Failed | 1 | 49 | Run_11-9_19-6-35 | Failed | 2018-11-09 | Approved | Script Error, OQ Script was modified
OQ | 40-26 Reference Data List Update - Item update (cancel creation) - Accepted by DS & SDS | Passed | 1 | 57 | Run_11-12_16-37-9 | Failed | 2018-11-14 | Approved | Code Issues
|  |  | 2 | 96 | Run_11-21_19-33-3 | Not Completed | 2018-11-21 | Obsolete | This was kept on hold by Tester 1 as he needed some clarificaiton. The tester 1 was later not available to continue the scirpt hence, this script was marked obsolete and re-executed by another tester
|  |  |  | 104 | Run_11-22_20-14-56 | Passed | 2018-11-22 | Approved | N/A
OQ | 40-27 Reference Data List Update - Item Update (cancel creation) - Record Locked | Passed | 1 | 46 | Run_11-9_18-19-16 | Passed | 2018-11-09 | Approved | N/A
OQ | 40-28 Reference Data List Update - Item Update (cancel creation) - Rejected by DS | Failed | 1 | 47 | Run_11-9_18-27-34 | Failed | 2018-11-09 | Approved | Script Error, OQ Script was modified
OQ | 40-29 Reference Data List Update - Item Update (golden definition) - Rejected by DS | Passed | 1 | 51 | Run_11-9_19-58-43 | Failed | 2018-11-09 | Approved | Code Issues
|  |  | 2 | 102 | Run_11-22_18-45-3 | Passed | 2018-11-22 | Approved | N/A
OQ | 40-30 Reference Data List Update - Item Update (golden definition) - Accepted by DS & Rejected by SDS | Failed | 1 | 52 | Run_11-9_20-10-53 | Failed | 2018-11-09 | Approved | Script Error, OQ Script was modified
OQ | 40-31 Reference Data List Update - Item Update (golden definition) - Accepted by DS & SDS | Failed | 1 | 54 | Run_11-9_20-56-53 | Failed | 2018-11-14 | Approved | Code Issues
|  | Passed | 2 | 103 | Run_11-22_19-26-1 | Passed | 2018-11-22 | Approved | N/A
OQ | 40-32 Reference Data List Update - Item Update (golden definition) - Record locked | Failed | 1 | 50 | Run_11-9_19-24-27 | Failed | 2018-11-09 | Approved | Script Error, OQ Script was modified
OQ | 40-33 Reference Data List Update - Item Update - Accepted by DS & Rejected by SDS | Passed | 1 | 60 | Run_11-12_18-15-39 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-34 Reference Data List Update - Item Update - Accepted by DS and & SDS | Passed | 1 | 61 | Run_11-12_19-52-19 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-35 Reference Data List Update - Item Update - Record Locked | Passed | 1 | 58 | Run_11-12_16-49-33 | Passed | 2018-11-12 | Approved | N/A
OQ | 40-36 Reference Data List Update - Item Update - Rejected by DS | Passed | 1 | 59 | Run_11-12_17-13-52 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-37 Reference Data List Update - Update Request - Accepted by SDS & SME | Passed | 1 | 65 | Run_11-12_21-48-33 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-38 Reference Data List Update - Update Request - Accepted by SDS & Rejected by SME | Failed | 1 | 64 | Run_11-12_21-35-1 | Failed | 2018-11-12 | Approved | Script Error, OQ Script was modified
OQ | 40-39 Reference Data List Update - Update Request - Rejected by SDS | Passed | 1 | 63 | Run_11-12_20-46-42 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-40 Reference Data List Update - Record Locked | Passed | 1 | 62 | Run_11-12_20-35-52 | Passed | 2018-11-12 | Approved | N/A
OQ | 40-41 BR WF-10 | Passed | 1 | 19 | Run_11-8_14-17-44 | Failed | 2018-11-09 | Approved | Code Issues
|  |  | 2 | 93 | Run_11-21_16-58-48 | Passed | 2018-11-21 | Approved | N/A
OQ | 40-42 BR WF-13 | Passed | 1 | 32 | Run_11-9_10-48-7 | Passed | 2018-11-09 | Approved | N/A
OQ | 40-43 BR WF-02 | Passed | 1 | 33 | Run_11-9_11-4-7 | Passed | 2018-11-09 | Approved | N/A
OQ | 40-44 BR-GDD 01 | Passed | 1 | 34 | Run_11-9_11-17-5 | Passed | 2018-11-09 | Approved | N/A
OQ | 40-45 BR GDD 03 | Passed | 1 | 35 | Run_11-9_12-8-28 | Passed | 2018-11-09 | Approved | N/A
OQ | 40-46 BR GDD 04 | Failed | 1 | 36 | Run_11-9_12-16-39 | Failed | 2018-11-09 | Approved | Script Error, OQ Script was modified
OQ | 40-47 BR GDD 05 | Passed | 1 | 37 | Run_11-9_12-47-40 | Not Completed | 2018-11-09 | Obsolete | Run was cancelled on purpose as the tester needed a clarification
|  |  |  | 38 | Run_11-9_12-48-49 | Passed | 2018-11-09 | Approved | N/A
OQ | 40-48 BR GDD 06 | Passed | 1 | 39 | Run_11-9_13-2-46 | Passed | 2018-11-09 | Approved | N/A
OQ | 40-49 BR GDD 07 | Passed | 1 | 41 | Run_11-9_13-11-2 | Passed | 2018-11-13 | Approved | N/A
OQ | 40-50 BR GDD 08 | Passed | 1 | 66 | Run_11-13_9-52-51 | Not Completed | 2018-11-13 | Obsolete | Run was cancelled on purpose as the tester needed a clarification
|  |  |  | 87 | Run_11-14_18-40-40 | Passed | 2018-11-14 | Approved | N/A
OQ | 40-51 BR GDD 09 | Passed | 1 | 67 | Run_11-13_11-8-42 | Passed | 2018-11-13 | Approved | N/A
OQ | 40-52 BR GDD 11 | Passed | 1 | 70 | Run_11-13_14-5-3 | Passed | 2018-11-13 | Approved | N/A
OQ | 40-53 BR GDD-12 | Passed | 1 | 71 | Run_11-13_14-38-26 | Failed | 2018-11-13 | Approved | Code Issues
|  |  | 2 | 92 | Run_11-21_16-52-3 | Passed | 2018-11-21 | Approved | N/A
OQ | 40-54 BR GDD 13 | Passed | 1 | 72 | Run_11-13_15-46-27 | Passed | 2018-11-13 | Approved | N/A
OQ | 40-55 BR GDD 14 | Failed | 1 | 74 | Run_11-13_16-53-13 | Failed | 2018-11-13 | Approved | Code Issues
|  |  | 2 | 101 | Run_11-22_15-32-41 | Failed | 2018-11-22 | Approved | Script Error, OQ Script was modified
OQ | 40-56 BR GDD 15 | Passed | 1 | 73 | Run_11-13_16-40-10 | Passed | 2018-11-13 | Approved | N/A
OQ | 40-57 BR GDD 16 | Failed | 1 | 78 | Run_11-13_17-36-54 | Failed | 2018-11-13 | Approved | Script Error, OQ Script was modified
OQ | 40-58 BR GDD 17 | Failed | 1 | 77 | Run_11-13_17-25-15 | Failed | 2018-11-13 | Approved | Script Error, OQ Script was modified
OQ | 40-59 BR GDD 18 | Passed | 1 | 79 | Run_11-13_19-31-26 | Failed | 2018-11-13 | Approved | Code Issues
|  |  | 2 | 91 | Run_11-21_16-24-24 | Passed | 2018-11-21 | Approved | N/A
OQ | 40-60 BR GDD 19 | Passed | 1 | 75 | Run_11-13_16-54-2 | Passed | 2018-11-13 | Approved | N/A
OQ | 40-61 Historization | Passed | 1 | 21 | Run_11-8_15-50-17 | Failed | 2018-11-08 | Approved | Code Issues
|  |  | 2 | 98 | Run_11-22_13-24-42 | Passed | 2018-11-22 | Approved | Code Issues
OQ | 40-62 Search options | Passed | 1 | 25 | Run_11-8_17-4-22 | Passed | 2018-11-08 | Approved | N/A
OQ | 40-63 BR GDD 20 | Passed | 1 | 55 | Run_11-12_15-14-43 | Passed | 2018-11-12 | Approved | N/A
OQ | 40-64 BR GDD 21 | Passed | 1 | 56 | Run_11-12_15-41-12 | Passed | 2018-11-12 | Approved | N/A
OQ | 40-65 Data Transfer to MDM | Passed | 1 | 68 | Run_11-13_11-28-44 | Not Completed | 2018-11-13 | Obsolete | Issue with Proton, hence had to cancel the script execution
|  |  |  | 85 | Run_11-14_15-34-25 | Not Completed | 2018-11-14 | Obsolete | Run was cancelled on purpose as the tester needed a clarification
|  |  | 1 | 89 | Run_11-15_15-20-56 | Failed | 2018-11-15 | Approved | Code Issues
|  |  | 2 | 99 | Run_11-22_14-42-50 | Passed | 2018-11-23 | Approved | N/A
OQ | 40-66 System Connection to MDM through API GW | Passed | 1 | 69 | Run_11-13_14-1-14 | Passed | 2018-11-13 | Obsolete | The tester had accidentally executed this script on dev environment as against being executed on QA environment
|  |  |  | 86 | Run_11-14_15-37-6 | Passed | 2018-11-15 | Approved | N/A
UAT | 1.0 - MDM Import Data | Passed | 1 |  | Run_12-3_18-0-42 | Failed | 2018-12-03 | Approved | Data is not displayed during the worfklow steps for approving or rejecting
|  |  | 2 |  | Run_12-5_17-36-13 | Not Completed | 2018-12-05 | Obsolete
[5 empty] | Run_12-5_17-53-47 | Passed | 2018-12-05 | Approved | N/A
UAT | 2.0 - Verify Entity Creation | Failed | 1 |  | Run_11-30_14-6-13 | Failed | 2018-11-30 | Approved | Configuration and business rule changes are required to handle spaces entered in the code appropriately
|  |  | 2 |  | Run_12-5_20-51-24 | Failed | 2018-12-05 | Approved
UAT | 3.0 Modify List-Item | Failed | 1 |  | Run_12-3_5-16-54 | Failed | 2018-12-03 | Approved | Needs configuration and business rule changes to increase the search threshold and increase the scope of data to be compared Email address configured in the system tobe changed to Adriana's email address
|  |  | 2 |  | Run_12-5_22-25-4 | Failed | 2018-12-05 | Approved
UAT | 4.0 - Match | Passed | 1 |  | Run_12-3_6-42-20 | Failed | 2018-12-03 | Approved | Needs configuration and business rule changes to remove spaces during comparison for duplciate checks
|  |  | 2 |  | Run_12-6_6-31-42 | Passed | 2018-12-06 | Approved | N/A
UAT | 5.0 External Source Hierarchy List | Failed | 1 |  | Run_11-30_13-21-42 | Failed | 2018-11-30 | Approved | Needs code change, change to the way platform handles the id and code association
|  |  | 2 |  | Run_12-6_7-21-49 | Failed | 2018-12-06 | Approved
UAT | 6.0 - History | Passed | 1 |  | Run_12-3_17-6-55 | Passed | 2018-12-03 | Approved | N/A
UAT | 7.0 - Audit Trail | Passed | 1 |  | Run_12-3_17-45-26 | Passed | 2018-12-03 | Approved | N/A

## Test Summary (ER 1)
Test Type | Test: Test Name | Test: Overall Status | Execution Round | Run ID | Run Name | Run: Execution Status | Run: Exec Date | Approval Status | Comment
IQ | GDD Platform IQ | Passed | ER round 1 |  | Run_12-11_16-52-24 | Passed | 2018-12-11 | Approved | N/A
IQ | SSL IQ | Passed | ER round 1 |  | Run_12-11_18-58-45 | Passed | 2018-12-11 | Approved | N/A
IQ | GDD - Web IQ |  | ER round 1 |  | Run_12-21_14-51-16 | Not Completed | 2018-12-21 | Obsolete | Reason? [MB]: Issue with Proton, hence had to cancel the script execution
[5 empty] | Run_12-21_15-16-20 | Passed | 2018-12-21 | Approved | N/A
|  |  | ER round 2 |  | Run_1-8_14-37-1 | Passed | 2019-01-08 | Approved | N/A
|  |  | ER round 3 |  | Run_1-16_11-39-48 | Passed | 2019-01-16 | Approved | N/A
|  |  | ER round 4 |  | Run_2-19_20-29-20 | Passed | 2019-02-19 | Approved | N/A
OQ | 40-68 BR-WF 29 | Failed | ER round 1 |  | Run_12-24_7-13-1 | Failed | 2018-12-26 | Approved | Re-tested as Passed as part of the UAT [MB] - Run was failed as the tester identified a functional defect (Defect ID - 70). Defect-70 and the complete functionality of "40-68 BR-WF 29" retested as part of "40-93 SME Permission Verification - List Deletion Request - Requested by SME" in ER Round 2 and stored all the evidences.
OQ | 40-69 BR GDD 17 | Passed | ER round 1 |  | Run_12-24_8-0-20 | Passed | 2018-12-24 | Approved | N/A
OQ | 40-70 BR-GDD 19 | Passed | ER round 1 |  | Run_12-24_9-10-6 | Passed | 2018-12-24 | Approved | N/A
OQ | 40-71 BR GDD 25 | Passed | ER round 1 |  | Run_12-24_11-21-10 | Passed | 2018-12-24 | Approved | N/A
OQ | 40-72 - Removal of BR GDD 15 | Passed | ER round 1 |  | Run_12-24_11-30-36 | Passed | 2018-12-24 | Approved | N/A
OQ | 40-76 Hide matching fields in the comparison screen during Item update Workflow | Passed | ER round 1 |  | Run_12-24_11-46-24 | Passed | 2018-12-28 | Approved | N/A
OQ | 40-77 Rename GDD to Reference Data for the dataspace | Passed | ER round 1 |  | Run_12-24_13-39-49 | Passed | 2018-12-24 | Approved | N/A
OQ | 40-79 public access (user 521) | Passed | ER round 1 |  | Run_12-24_14-32-24 | Not Completed | 2018-12-26 | Obsolete | Reason? [MB]: Run was cancelled as tester needed more clarification
[5 empty] | Run_12-26_17-47-37 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-9_13-40-48 | Passed | 2019-01-09 | Approved | N/A
OQ | 40-81 Workflow rejection - List Updation Request - Rejected by SDS | Passed | ER round 1 |  | Run_12-25_9-54-8 | Passed | 2018-12-25 | Obsolete | N/A
OQ | 40-82 Workflow rejection - List Updation Request - Rejected by SME | Passed | ER round 1 |  | Run_12-25_11-50-24 | Passed | 2018-12-25 | Obsolete | N/A
OQ | 40-83 Workflow rejection - List Creation Request - Rejected by SDS | Passed | ER round 1 |  | Run_12-25_12-31-22 | Passed | 2018-12-25 | Obsolete | N/A
OQ | 40-84 Workflow rejection - List Creation Request - Rejected by SME | Passed | ER round 1 |  | Run_12-25_15-46-21 | Passed | 2018-12-25 | Obsolete | N/A
OQ | 40-85 Workflow rejection - List Deletion Request - Rejected by SDS | Passed | ER round 1 |  | Run_12-26_7-57-10 | Passed | 2018-12-26 | Obsolete | N/A
OQ | 40-86 Workflow rejection - List Deletion Request - Rejected by SME | Passed | ER round 1 |  | Run_12-26_8-17-19 | Passed | 2018-12-26 | Obsolete | N/A
OQ | 40-87 Workflow rejection - List Reactivation Request - Rejected by SDS | Passed | ER round 1 |  | Run_12-26_8-41-38 | Passed | 2018-12-26 | Obsolete | N/A
OQ | 40-88 Workflow rejection - List Reactivation Request - Rejected by SME | Passed | ER round 1 |  | Run_12-26_10-15-56 | Passed | 2018-12-26 | Obsolete | N/A
OQ | 40-89 Explicit selection of a Approver from drop down | Passed | ER round 1 |  | Run_12-26_10-36-56 | Passed | 2018-12-26 | Obsolete | N/A
OQ | 40-73 Reactivation list Workflow - Accepted by SDS and SME | Passed | ER round 1 |  | Run_12-26_12-2-19 | Passed | 2018-12-26 | Approved | N/A
OQ | 40-67 Historization and Code field in Applications table | Passed | ER round 1 |  | Run_12-26_15-8-28 | Passed | 2018-12-26 | Approved | N/A
OQ | 40-91 SME Permission Verification - List Updation Request - Requested by SME | Passed | ER round 1 |  | Run_12-26_15-32-22 | Not Completed | 2018-12-26 | Obsolete | Reason? [MB]: Run was cancelled as tester needed more clarification
[5 empty] | Run_12-26_16-6-58 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-10_16-55-43 | Passed | 2019-01-10 | Approved | N/A
|  |  | ER round 3 |  | Run_1-17_13-25-36 | Passed | 2019-01-17 | Approved | N/A
OQ | 40-92 SME Permission Verification - List Creation Request - Requested by SME | Passed | ER round 1 |  | Run_12-26_16-14-18 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-11_6-38-10 | Passed | 2019-01-11 | Approved | N/A
OQ | 40-80 Comestic change during matching workfow (Item update) | Passed | ER round 1 |  | Run_12-26_16-15-20 | Passed | 2018-12-26 | Approved | N/A
OQ | 40-93 SME Permission Verification - List Deletion Request - Requested by SME | Passed | ER round 1 |  | Run_12-26_16-22-17 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-11_8-22-50 | Passed | 2019-01-11 | Approved | N/A
OQ | 40-94 SME Permission Verification - List Reactivation Request - Requested by SME | Passed | ER round 1 |  | Run_12-26_16-25-56 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-11_9-51-15 | Passed | 2019-01-11 | Approved | N/A
OQ | 40-95 SME Permission Verification - Item Creation Request - Requested by SME | Passed | ER round 1 |  | Run_12-26_16-40-26 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-11_10-59-54 | Passed | 2019-01-11 | Approved | N/A
OQ | 40-74 Reactivation Workflow - Rejected by SDS | Passed | ER round 1 |  | Run_12-27_11-31-31 | Failed | 2018-12-27 | Approved | Failed and re-tested right next day?? [MB}: Failed the run as tester identified inappropriate test steps during execution
[5 empty] | Run_12-27_11-15-22 | Not Completed | 2018-12-28 | Obsolete | Reason? [MB]: Run was cancelled as tester needed more clarification
|  |  | ER round 2 |  | Run_1-9_8-3-17 | Passed | 2019-01-09 | Approved | N/A
OQ | 40-75 Reactivation workflow - Rejected by SME | Passed | ER round 1 |  | Run_12-27_11-32-41 | Failed | 2018-12-27 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-9_9-53-9 | Passed | 2019-01-09 | Approved | N/A
|  |  | ER round 3 |  | Run_1-16_15-56-3 | Passed | 2019-01-17 | Approved | Why re-tested when it passed during ER - round 2? [MB]: After round 2 some of the test steps were modified therefore re-tested again in Round 3.
OQ | 40-78 Search on list and Item filtering using applications and permissions criteria | Passed | ER round 1 |  | Run_12-27_10-54-36 | Not Completed | 2018-12-27 | Obsolete | Reason? [MB]: Run was cancelled as tester needed more clarification
[5 empty] | Run_12-27_10-55-58 | Failed | 2018-12-27 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
| 40-78 Search on list and tem filtering using applications |  | ER round 2 |  | Run_1-9_10-55-56 | Passed | 2019-01-09 | Approved | N/A
OQ | 40-81 Workflow rejection - List Updation Request - Rejected by SDS | Passed | ER round 1 |  | Run_12-26_17-50-53 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-9_13-10-50 | Passed | 2019-01-09 | Approved | N/A
OQ | 40-82 Workflow rejection - List Updation Request - Rejected by SME | Passed | ER round 1 |  | Run_12-26_17-56-18 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-9_13-59-4 | Passed | 2019-01-09 | Approved | N/A
OQ | 40-83 Workflow rejection - List Creation Request - Rejected by SDS | Passed | ER round 1 |  | Run_12-26_17-53-12 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-9_14-40-56 | Passed | 2019-01-09 | Approved | N/A
OQ | 40-84 Workflow rejection - List Creation Request - Rejected by SME | Passed | ER round 1 |  | Run_12-26_17-57-51 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-10_7-54-25 | Passed | 2019-01-10 | Approved | N/A
|  |  | ER round 3 |  | Run_1-17_14-53-19 | Passed | 2019-01-18 | Approved | Why re-tested when it passed during ER - round 2? [MB]: After round 2 some of the test steps were modified therefore re-tested again in Round 3.
OQ | 40-85 Workflow rejection - List Deletion Request - Rejected by SDS | Passed | ER round 1 |  | Run_12-26_17-54-5 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-10_10-59-12 | Passed | 2019-01-10 | Approved | N/A
OQ | 40-86 Workflow rejection - List Deletion Request - Rejected by SME | Passed | ER round 1 |  | Run_12-26_17-59-10 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-10_12-27-40 | Passed | 2019-01-10 | Approved | N/A
OQ | 40-87 Workflow rejection - List Reactivation Request - Rejected by SDS | Passed | ER round 1 |  | Run_12-26_17-55-24 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-10_13-21-23 | Passed | 2019-01-10 | Approved | N/A
OQ | 40-88 Workflow rejection - List Reactivation Request - Rejected by SME | Passed | ER round 1 |  | Run_12-26_18-1-5 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-10_15-21-10 | Passed | 2019-01-10 | Approved | N/A
OQ | 40-89 Explicit selection of a Approver from drop down | Passed | ER round 1 |  | Run_12-26_18-8-10 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-12_9-39-15 | Passed | 2019-01-12 | Approved | N/A
|  |  | ER round 3 |  | Run_1-18_8-5-47 | Passed | 2019-01-18 | Approved | Why re-tested when it passed during ER - round 2? [MB]: After round 2 some of the test steps were modified therefore re-tested again in Round 3.
OQ | 40-90 Summary of recent import action | Passed | ER round 1 |  | Run_12-26_18-36-37 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-12_10-14-21 | Passed | 2019-01-12 | Approved | N/A
OQ | 40-96 SDS Permission Verification - Item Creation Request - Requested by SDS | Passed | ER round 1 |  | Run_12-26_17-5-22 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-11_14-56-4 | Passed | 2019-01-11 | Approved | N/A
|  |  | ER round 3 |  | Run_1-17_9-3-30 | Passed | 2019-01-17 | Approved | Why re-tested when it passed during ER - round 2? [MB]: After round 2 some of the test steps were modified therefore re-tested again in Round 3.
OQ | 40-97 Workflow verification --List Creation | Passed | ER round 1 |  | Run_12-26_18-11-52 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-11_19-57-31 | Failed | 2019-01-11 | Approved | [MB]: Failed the run as tester identified a functional defect (Defect ID - 77)
|  |  | ER round 3 |  | Run_1-16_16-7-4 | Passed | 2019-01-17 | Approved | N/A
OQ | 40-98 Matching algorithm Verification - List Creation | Passed | ER round 1 |  | Run_12-26_18-21-42 | Failed | 2018-12-26 | Approved | [MB}: Failed the run as tester identified inappropriate test steps during execution
|  |  | ER round 2 |  | Run_1-11_21-35-5 | Passed | 2019-01-11 | Approved | N/A
|  |  | ER round 3 |  | Run_1-17_8-41-6 | Passed | 2019-01-17 | Approved | Why re-tested when it passed during ER - round 2? [MB] :After round 2 some of the test steps were modified therefore re-tested again in Round 3.
UAT | 40-67 Historization and Code field in Applications table | Passed | ER round 1 |  | Run_1-28_11-57-2 | Passed | 2019-02-01 | Approved | N/A
UAT | 40-68 BR-WF 29 | Passed | ER round 1 |  | Run_1-29_22-13-0 | Passed | 2019-01-29 | Approved | N/A
UAT | 40-69 BR GDD 17 | Passed | ER round 1 |  | Run_1-22_18-6-49 | Passed | 2019-01-22 | Approved | N/A
UAT | 40-70 BR-GDD 19 | Passed | ER round 1 |  | Run_1-22_18-32-34 | Passed | 2019-01-22 | Approved | N/A
UAT | 40-71 BR GDD 25 | Passed | ER round 1 |  | Run_1-23_7-34-20 | Passed | 2019-01-23 | Approved | N/A
UAT | 40-72 - Removal of BR GDD 15 | Passed | ER round 1 |  | Run_1-23_7-44-13 | Passed | 2019-01-23 | Approved | N/A
UAT | 40-73 Reactivation list Workflow - Accepted by SDS and SME | Passed | ER round 1 |  | Run_1-23_14-2-13 | Failed | 2019-01-24 | Approved | [MB}: Failed the run as tester executed the OQ with wrong test data (Defect ID- 84)
|  |  | ER round 2 |  | Run_2-10_12-38-16 | Failed | 2019-02-10 | Approved | [MB]: Failed the run as tester identified a functional defect (Defect ID - 82)
|  |  | ER round 3 |  | Run_2-22_15-27-51 | Passed | 2019-02-22 | Approved | N/A
UAT | 40-74 Reactivation Workflow - Rejected by SDS | Passed | ER round 1 |  | Run_1-24_21-24-41 | Passed | 2019-01-24 | Approved | N/A
UAT | 40-75 Reactivation workflow - Rejected by SME | Passed | ER round 1 |  | Run_1-24_22-1-54 | Failed | 2019-01-24 | Approved | [MB]: Failed the run as tester identified a functional defect (Defect ID - 79)
|  |  | ER round 2 |  | Run_2-10_11-53-53 | Passed | 2019-02-10 | Approved | N/A
|  |  | ER round 3 |  | Run_2-22_10-46-35 | Passed | 2019-02-22 | Approved | Why re-tested when it passed during ER - round 2? [MB] :After round 2 some of the test steps were modified therefore re-tested again in Round 3.
UAT | 40-76 Hide matching fields in the comparison screen during Item update Workflow | Passed | ER round 1 |  | Run_1-28_21-36-24 | Passed | 2019-01-29 | Approved | N/A
UAT | 40-77 Rename GDD to Reference Data for the dataspace | Passed | ER round 1 |  | Run_1-30_19-56-20 | Passed | 2019-01-30 | Approved | N/A
UAT | 40-78 Search on list and tem filtering using applications | Passed | ER round 1 |  | Run_1-24_20-30-23 | Passed | 2019-01-29 | Approved | N/A
UAT | 40-79 public access (user 521) | Passed | ER round 1 |  | Run_2-1_15-18-47 | Failed | 2019-02-01 | Approved | [MB}: Failed the run as tester identified a functional defect - (Defect ID -81)
|  |  | ER round 3 |  | Run_2-22_10-19-35 | Passed | 2019-02-22 | Approved | N/A
UAT | 40-80 Comestic change during matching workfow (Item update) | Passed | ER round 1 |  | Run_1-30_20-1-25 | Passed | 2019-01-30 | Approved | N/A
UAT | 40-81 Workflow rejection - List Updation Request - Rejected by SDS | Passed | ER round 1 |  | Run_1-30_20-12-46 | Failed | 2019-01-30 | Approved | [MB}: Failed the run as tester identified a functional defect - (Defect ID -80)
|  |  | ER round 2 |  | Run_2-10_11-26-50 | Passed | 2019-02-10 | Approved | N/A
|  |  | ER round 3 |  | Run_2-22_15-6-8 | Passed | 2019-02-22 | Approved | Why re-tested when it passed during ER - round 2? [MB] :After round 2 some of the test steps has been modified therefore re-tested again in Round 3.
UAT | 40-82 Workflow rejection - List Updation Request - Rejected by SME | Passed | ER round 2 |  | Run_2-11_1-34-49 | Passed | 2019-02-11 | Approved | N/A
UAT | 40-83 Workflow rejection - List Creation Request - Rejected by SDS | Passed | ER round 2 |  | Run_2-11_1-43-29 | Passed | 2019-02-11 | Approved | N/A
UAT | 40-84 Workflow rejection - List Creation Request - Rejected by SME 1 | Passed | ER round 2 |  | Run_2-11_2-4-14 | Passed | 2019-02-11 | Approved | N/A
UAT | 40-85 Workflow rejection - List Deletion Request - Rejected by SDS | Passed | ER round 2 |  | Run_2-11_2-11-40 | Passed | 2019-02-11 | Approved | N/A
UAT | 40-86 Workflow rejection - List Deletion Request - Rejected by SME | Passed | ER round 2 |  | Run_2-11_2-23-39 | Passed | 2019-02-11 | Approved | N/A
UAT | 40-87 Workflow rejection - List Reactivation Request - Rejected by SDS | Passed | ER round 2 |  | Run_2-10_12-22-48 | Passed | 2019-02-10 | Approved | N/A
UAT | 40-88 Workflow rejection - List Reactivation Request - Rejected by SME | Passed | ER round 2 |  | Run_2-10_12-29-38 | Passed | 2019-02-10 | Approved | N/A
UAT | 40-89 Explicit selection of a Approver from drop down | Passed | ER round 1 |  | Run_2-1_18-55-9 | Passed | 2019-02-01 | Approved | N/A
UAT | 40-90 Summary of recent import action | Passed | ER round 1 |  | Run_1-30_20-36-33 | Passed | 2019-01-30 | Approved | N/A
UAT | 40-91 SME Permission Verification - List Updation Request - Requested by SME | Passed | ER round 1 |  | Run_1-30_21-13-33 | Passed | 2019-01-30 | Approved | N/A
UAT | 40-92 SME Permission Verification - List Creation Request - Requested by SME | Passed | ER round 1 |  | Run_2-1_17-27-25 | Passed | 2019-02-01 | Approved | N/A
UAT | 40-93 SME Permission Verification - List Deletion Request - Requested by SME | Passed | ER round 1 |  | Run_2-1_17-44-57 | Passed | 2019-02-01 | Approved | N/A
UAT | 40-94 SME Permission Verification - List Reactivation Request - Requested by SME | Passed | ER round 1 |  | Run_2-1_18-39-6 | Passed | 2019-02-01 | Approved | N/A
UAT | 40-95 SME Permission Verification - Item Creation Request - Requested by SME | Passed | ER round 1 |  | Run_2-1_18-8-57 | Passed | 2019-02-01 | Approved | N/A
UAT | 40-96 SDS Permission Verification - Item Creation Request - Requested by SDS | Passed | ER round 1 |  | Run_2-1_18-25-19 | Passed | 2019-02-01 | Approved | N/A
UAT | 40-97 Workflow verification --List Creation | Passed | ER round 1 |  | Run_1-28_21-17-17 | Passed | 2019-01-29 | Approved | N/A
UAT | 40-98 Matching algorithm Verification - List Creation | Passed | ER round 1 |  | Run_1-28_20-56-26 | Passed | 2019-01-28 | Approved | N/A